## Prioritization Count
Priority | Count of Priority
High | 21
Medium | 33
Low | 60

## Comments
Item | Section | Subsection | Comment | Commenter | Status | Priority | Resolution
1 | I | A | Not clear if the roles are laid out for these other tools below. | Rachel Hemphill | Revised in latest draft | Low | Added responsibility in roles below.
2 | I | C.7 | We also suggest that the model governance framework include a requirement to create backup copies of the current and previous version of the model, in case of model corruption or data loss. | RRC | Revised in latest draft | Low | See section 7.G
3 | I | C.9 | While Section I.C.9 mentions access controls, we suggest that Section I.C also cover storage, i.e., where models are stored, perhaps referencing the three separate modeling environments used by Conning, described in Section VIII.D. | RRC | Revised in latest draft | Low | See section 7.G
4 | II | A | In addition to the roles mentioned in Section II.A, we recommend the addition of the role of Model Designer. We believe that the NAIC/LATF Committee would be assigned this role and would be responsible for requesting specific changes or enhancements to the model to meet desired regulatory purposes. The Model Designer should be independent of the Model Developer. This role could also be mentioned in Section I.C component #1 and the first paragraph of Section II.A. | RRC | Revised in latest draft | Low | Added this role into the model steward role that is taken by the GOES (E/A) Subgroup
5 | II | A | Overall, this table does not seem fully applicable to all models in the Model Inventory (particularly, the “ancillary tools”). ⦁ For the models that produce the Basic and Robust Data Sets, as well as the API tool, Conning serves as the “First Line of Defense”: they develop the models, create documentation, and perform independent peer review. Given Conning develops and owns the model, we need “Second Line of Defense” to perform some technical review and/or substantiate testing for reasonability or unintended consequence check, not just control review. This role is typical for a company with a sound and well-defined risk management framework. ⦁ These roles are not clear for the other tools in the Model Inventory File. If the NAIC owns and develops those tools, then there is no clear delineation between the first - and second-line functions. Who provides oversight? Independent review? | ACLI | Revised in latest draft | High | Added responsibility to develop and maintain ancillary tools.
6 | II | A | These are the Roles and Responsibilities for all models (including analysis files)? They seem specific to the GEMS implementation. | Rachel Hemphill | Revised in latest draft | Low | Added responsibility to develop and maintain ancillary tools
7 | II | A | We recommend that the high-level responsibilities include model validation (as described in Section V.B) and managing the modeling environments, conducting testing, and completing change documentation to meet governance requirements (as described in Section VIII.D). | RRC | Revised in latest draft | Low | Updated
8 | II | A | We also recommend that the Model Developer be the owner of any new code that is required for the software to meet NAIC model specifications. | RRC | Revised in latest draft | Low | Updated
9 | II | A | We suggest that the Model Developer will incorporate change requests from the Model Steward into the GEMS© software rather than “incorporate NAIC requirements”, as all requirements should flow through the Model Steward. | RRC | Revised in latest draft | Low | Updated
10 | II | A | In my experience, the model owner is typically a leader in the area that relies on the model for business outcomes (i.e., the person who uses the model for decision making and cares about its results). The model owner has overall accountability for the model and is the decision maker on intended purpose, strategy, priorities, usage, etc., including initiating the selection of new vendors and/or models. LATF or the GOES Subgroup would be the natural candidates for this role. | Connie Tang | Unaddressed | Low
11 | II | A | While Conning’s Professional Services Team may be the product owner for GEMS software development and “own” the running of the model / generation of the model output, I would not expect them to be the GOES model owner unless we are adopting a more colloquial definition of "model owner" (i.e., the point of contact or person responsible (i.e., “hands on keyboard”) for implementing and running the model). Some of the confusion may stem from software development life cycle (SDLC) vs. model development life cycle (MDLC) terms and considerations, so we may need to be careful about the context in which we use terms like “developer” or “owner.” Elaborating on roles and responsibilities (e.g., through tools such as a RACI matrix) may alleviate potential terminology confusion. Examples of activities to explicitly identify include: ⦁ Roles, responsibilities, and sign-off processes for initial (and future) vendor review and selection since vendor selection is a key part of the GOES process and may be a de facto and highly consequential actuarial modeling and assumption decision if the vendor only supports one particular model form. ⦁ Defining intended purpose, priorities, stylized facts, acceptance criteria, and other requirements (e.g., for ancillary tools) ⦁ Identifying, recommending, approving, and implementing a model form / structure; relevant calibration data, methodologies, and targets; SERT scenario definitions and methodologies; scenario selection counts, dimensions, methodologies; diagnostic and summary metrics; etc. This additional detail would also address a fundamental question and clarify professionalism responsibilities (e.g., around expertise and potential conflicts of interest): Is the GOES vendor a software vendor acting at LATF’s direction or a consultant providing Actuarial Services by recommending material valuation assumptions? Clear divisions of labor and expectations are critical when two parties (i.e., LATF, Conning) are fulfilling three conceptual roles: regulator / sponsor, actuarial consultant / PBR economic assumption expert, and software vendor. | Connie Tang | Unaddressed | Low
12 | II | A | We suggest that user acceptance testing (“UAT”) also include Model Users (i.e., Industry and State Insurance Regulators), even if from an oversight perspective. | RRC | Revised in latest draft | Medium | Udpated model user role
13 | II | A | Regarding model stewardship, Conning should have some role for ancillary roles, such as model developer. | ACLI | Revised in latest draft | Low | Additional information added on Conning’s role as model developer
14 | II | A | Responsibilities of the Model Steward role should include accuracy, quality, and fitness of the model, in addition to the governance of the model. We would expect that the Model Steward would be responsible for collecting input from the Model Users (i.e., Industry and State Insurance Regulators) on necessary upgrades. We recommend that Model Selection (as described in Section V.A) be included in the high-level responsibilities and that all NAIC requirements to be incorporated into the GEMS© software flow through the Model Steward. | RRC | Revised in latest draft | Medium | Updated section based on comments
15 | II | A | The model steward typically has more of a compliance and day-to-day implementation role (i.e., making sure that strategies, frameworks, policies set by the model owner or other authorities are followed). | Connie Tang | Revised in latest draft | Low | NAIC Support Staff can handle more of the day to day operations
16 | II | A | So is NAIC staff the Model developer and owner for the analysis tools? | Rachel Hemphill | Revised in latest draft | Low | Both Conning and NAIC will produce scenario statistics. NAIC producing and reviewing scenario statistics will allow for independent check of scenario files.
17 | II | A | In certain cases, the separation of duties is unclear (such as ownership/review of statistics). We think this should be more specific, especially in cases where there is ambiguity of duties between Conning and NAIC. | ACLI | Revised in latest draft | Low | Added information to clarify that NAIC and Conning will both produce scenario statistics.
18 | II | A | We suggest adding that they would also assist with UAT. | RRC | Revised in latest draft | Low | Added volunteer for field test role for model users.
19 | II | B | we believe that systemic risk should be mentioned along with the material financial impact since the GOES model will be used industry-wide. | RRC | Revised in latest draft | Low | Added mention of systemic risk to seciotn 4.B.
20 | II | B | The Sept. 25, 2024 GOES Subgroup call noted that Conning’s attestation in Section II.B is consistent with Sarbanes-Oxley (SOX) / Model Audit Rule (MAR) requirements. SOX/MAR attestations are usually provided after independent testing (e.g., by an auditor). Will such testing be required for GOES, or will this be a self-attestation (i.e., no independent testing)? If a company had developed or were running an economic scenario generator for material GAAP / statutory balances, the generator would likely be in scope for periodic independent testing. Companies outsourcing work affecting financial reporting often require service providers to have a third party audit and report on their controls (e.g., Service Organization Control (SOC 1) reports). | Connie Tang | Unaddressed | Medium | Suggest considering as day II item.
21 | II | B | It may also be helpful to include a graphical representation of the roles and responsibilities, for example in a process flow format. | RRC | Unaddressed | Low | Suggest considering for future versions
22 | II | B | Conning should have standard operating procedures, appropriate controls, and risk assessments for all its GOES-related processes. Given the importance of GOES and its more “black box” scenario production process, best practice would include formal review and/or testing of end-to-end processes and controls, an assessment / summary of results, and attestation. | Connie Tang | Revised in latest draft | High | Conning includes an attestation of controls performed to the NAIC with each scenario release.
23 | II | B | We recommend that an auditing process be included. This may include a System and Organization Controls 1 (“SOC 1”) report as part of the attestation provided to NAIC staff. We would recommend that it be provided at inception and every two to three years. This could also be included as part of the sign-off protocols in Section III.D. | RRC | Unaddressed | High | Suggest considering as day II item.
24 | II | B | Is documentation just an e-mail, or is there some checklist that gets initialed for each reviewed item and any commentary? | Rachel Hemphill | Revised in latest draft | Medium | Added in more detail on attestation document
25 | II | B | Regarding attestation, how is this performed and documented? We would support a checklist that gets initialed for each reviewed item and any commentary associated with the review. | ACLI | Revised in latest draft | Low | added more detail on attestation document.
26 | II | B | Is this review sufficient for the NAIC to be confident that the model is fit for use? | ACLI | Revised in latest draft | Low | Clarified that GOES (E/A) Subgroup determines that model is fit for use.
27 | II | B | Scenario statistics will play a key role in monitoring the appropriateness of the scenarios. The framework discusses the governance related to production and review of statistics but does not define those statistics themselves or who owns them. There needs to be a clearly defined list of statistics to validate against the criteria. Further, the guidance should also cover how NAIC validates the model statistics to the criteria without an explicitly defined range of acceptance. Are there clearly defined specifications detailing how the statistics are calculated? If not, this should be defined. Who produces the stats, the NAIC or Conning? And if Conning produces them, how does NAIC validate that the stats are correct? | ACLI | Revised in latest draft | High | NAIC to produce documentation of the acceptance criteria and statistics that they independently generate detailing the calculations, etc.
28 | II | B | How will sign off occur based on the statistics? | ACLI | Revised in latest draft | Medium | email
29 | II | B | As noted in Section V.A.2, judgement is involved in determining whether scenario sets are acceptable or need to be revised. Absent clear rules for determining whether scenario sets are acceptable, the GOES subgroup should also be involved in the decision. | ACLI | Unaddressed | Medium | GOES SG to handle acceptance criteria in multiple economic environments as a day II item to support NAIC Staff evaluation of scenario fit-for-purpose in materially different economic environments.
30 | II | B | NAIC should develop the inventory of statistics. We suggest interested parties have a say in the development of those statistics. | ACLI | Unaddressed | Low | NAIC to develop inventory of statistics documentation.
31 | II | B | Will there be publication of controls publicly? | ACLI | Addressed | Medium | NAIC to provide scenario review workpaper templates for feedback from interested parties.
32 | II | B | With all three responsibilities listed in this section, would there be an exposure and comment period for these items after new GOES is implemented? | ACLI | Revised in latest draft | Medium | Added more detail to indicate public notice and public meetings
33 | II | B | How will responsibility #1 (“All material non-routine updates to the model, such as model recalibrations”) be communicated widely? | ACLI | Revised in latest draft | low | Communications of changes will occur through the GOES (E/A) Subgroup distribution list.
34 | III | B | We recommend that reference to the Model Steward role be mentioned at the end of the first paragraph in Section III.B. For example, “As the Model Steward, the Subgroup will direct NAIC Staff as necessary to effectuate aspects of the Framework.” | RRC | Revised in latest draft | Low | Updated
35 | III | C | We assume that NAIC staff would not only develop the scenario review process but also perform a review of the statistics each time scenarios are produced. We recommend that this be clarified within the NAIC Staff responsibilities. | RRC | Revised in latest draft | Low | Clarifed
36 | III | C | Act under the direction of the GOES (E/A) Subgroup to support the implementation of the economic scenario generator as well as implement and monitor the model governance. | RRC | Revised in latest draft | Low | Made edit
37 | III | D.1 | The Robust Data Set is mentioned in Section III.D as having additional data fields, but this section does not mention what additional fields are available for a fee. We recommend adding this. | RRC | Revised in latest draft | Medium | references to robust data set have been removed
38 | III | D.2 | Here we are noting the “model user” role as “end user”. Maybe this is ok, since they are using the scenarios rather than the model(s) themselves? | Rachel Hemphill | Revised in latest draft | Low | replaced all End User phrase with model user
39 | III | D.3 | ACLI recommends at minimum a three-month trial period. | ACLI | Revised in latest draft | Low | Added reference to the planned release of scenarios starting 10/1
40 | III | D.3 | Validation reports need to show how well the model performs against acceptance criteria and stylized facts. It may be helpful to provide more detail on the process / thresholds to determine whether a scenario set is acceptable, while still allowing for appropriate use of judgment. | ACLI | Revised in latest draft | Low | Prototype dashboard to be discussed 10/29/25.
41 | III | D.3 | ACLI members would appreciate the posting all of the scenarios picker tools, values, and scenario subsets. | ACLI | Addressed | Low | The scenario selection tool is efficient at producing subsets. In testing on my 3-year old laptop it was able to produce a 1,000 scenario subset in about two minutes.
42 | III | D.3 | This is true for VM-21, but not VM-20. VM-20 would need to be changed. VM-20 will likely need to be updated either way due to the specific language not being correct with an external tool: “The smaller set of scenarios is generated using the scenario picker tool provided within the prescribed scenario generator,”. | Rachel Hemphill | Addressed | Medium | VM-20 has been updated
43 | III | D.3 | The GOES scenarios will be used for products with different risk profiles and sensitivity to one or more market risks. Therefore, the scenario selection tool should have the functionality to stratify on multiple dimensions (i.e., rates and equities). (The posted GOES tool stratifies on only one or the other.) | Connie Tang | Addressed | High | Can consider enhancements to the scenario selection tool as a day II item. Otherwise companies have the ability to use other tools or methodologies to selects scenarios provided they meet the requirements of the Valuation Manual.
44 | III | D.3 | There should be a well-defined communication, escalation, and fallback plan if something unexpected occurs during scenario generation (as well as a business continuation plan for other potential disruptions). Year-end and quarter-end valuations are typically the most critical and require tighter recovery / resolution times. | Connie Tang | Revised in latest draft | High | Added section II.C Fallback plan
45 | III | D.3 | We would like to better understand the escalation process, particularly in the following situations: ⦁ In what situations would NAIC pause the release of scenarios? How would the process be handled after escalation to reach resolution? ⦁ How should companies handle unintuitive scenarios or reserve or capital impacts? How would that escalation process look? | ACLI | Revised in latest draft | High | Added section II.C Fallback plan
46 | III | D.3 | Regarding the course of action if there will be a delay in posting scenarios, up to a one-day delay would be acceptable. If there is a significant issue identified after scenarios are posted, then there is a larger discussion to be had beyond having a contingency plan such as allowing companies to revert back to the previous month’s scenarios with any appropriate adjustments for starting conditions on the valuation date, e.g. replacing prior period initial yield curve with the current period. Another aspect to consider is that quarter end, month end, and year end also all have different levels of importance to companies so it will be crucial for there to be a detailed and pre-determined contingency plan if we cannot get scenarios in a timely manner. | ACLI | Revised in latest draft | High | Added section II.C Fallback plan
47 | III | D.3 | I would think in the case that this does occur, we need to be clear what the acceptable fallback would be (i.e. use the previous set of accepted scenarios) | Matt Cheung | Revised in latest draft | High | Added section II.C Fallback plan
48 | III | D.3 | Posting all scenario subsets companies might use is not practical, so posting the scenario selection tool is a good alternative. It may also be helpful to post ⦁ The scenarios or selected scenario numbers for a few key stratifications. (E.g., the scenario numbers for a 1,000 scenario interest rate-only set, 1,000 scenario equity- only set, and a 1,000 interest rate / equity set) ⦁ Scenario statistics tools so that companies can calculate and compare statistics for their subsets to the full 10,000 scenario set. | Connie Tang | Addressed | Medium | Scenario selection tool will be provided to create subsets.
49 | III | D.3 | While we believe that it may be possible to incorporate additional sensitivity scenarios that will satisfy most of the requests from regulators and rating agencies, we remain concerned about scenarios needed for both financial conditions testing and for making timely financial decisions, without having to compromise on the timing and amount of information available. We believe we will need to continue to use our internal generator for these purposes. | John Hancock | Addressed | Medium | NAIC is declining to provide additional sensitivities at this time.
50 | III | D.3 | Typical sensitivities may include up and down shocks on all key initial market inputs. This will require a complete inventory of the initial market conditions used in the GEMS interest rate, equity, and corporate models. For interest rates, the sensitivities could include both parallel and key rate shocks. We will need to understand and assess how well GEMS accommodates non-parallel sensitivities given initial curve fitting issues and the material, persistent impact of initial state variable selection / fitting on GOES scenarios. | Connie Tang | Addressed | Medium | NAIC is declining to provide additional sensitivities at this time.
51 | III | D.7 | Should we be addressing access to model documentation here (e.g., the NDA)? | Rachel Hemphill | Revised in latest draft | High | In section IX, we note how to access additional documentation (e.g. NDA).
52 | III | D.8 | Is this some future field test? Like, if we had some future VM-23? I am not sure what this means in the Model Governance Framework. | Rachel Hemphill | Revised in latest draft | Low | Added additional detail.
53 | III | E | Because of the substantial impact GOES will have on all life insurance activities, it is critical that the Subgroup provide clear communications and rationale behind its decisions. We would request the following to be included in the formal written governance and guidance: ⦁ The Subgroup and Conning should document decisions and rationale behind technical modifications to GOES. ⦁ Formal discussions and decisions on technical GOES issues should be conducted on public calls so industry can provide meaningful and useful feedback the regulators may want to consider in those discussions. ⦁ There may be times when it is appropriate to rely on the vendor for feedback without engaging the industry, and we would encourage the regulators to develop clear guidance on when that might be appropriate. | ACLI | Revised in latest draft | Medium | Added additional responsibilities to the GOES SG role
54 | III | E.1 | We believe that Subject Matter Experts and Interested Parties would bring any model or governance issues to the GOES (E/A) Subgroup for consideration. | RRC | Revised in latest draft | Low | updated
55 | IV | A | ACLI agrees with the note from regulators that it would be prudent to start out with all models listed in the Model Inventory File ranked as high risk. | ACLI | Addressed | Low | Nothing to do here.
56 | IV | B | Section B (Model Risk Rating) discusses the assignment of a risk rating and notes that all models listed in the Model Inventory File are currently ranked as high risk. The Exposure draft does not mention who is responsible for determining the risk rating on an ongoing basis, or the frequency at which the rating should be reviewed. We recommend that the appropriate governance role be assigned this responsibility. We also recommend including the model risk rating responsibility in the governance roles in Section II.A. | RRC | Revised in latest draft | Low | Noted it is the GOES S's responsibility.
57 | IV | B | To strengthen governance, additional detail and clarification could be added on how certain aspects of the framework will be applied. For example, the following would be helpful: Defined methodology for determining the model risk rating and clarification on how governance requirements will vary by rating or by complexity/materiality of a model change. | ACLI | Unaddressed | Medium
58 | IV | B | Typically, a model governance policy establishes quantitative and qualitative criteria (and other considerations) for high-, medium-, and low-risk classifications. Each classification is associated with risk-based testing and review requirements. This document provides the rationale for a “high” classification without defining “low” and “medium” because the GOES model is clearly high-risk overall. However, not every model component or tool within GOES may be high risk, so establishing explicit classification criteria may facilitate more efficient, risk-based activity. | Connie Tang | Unaddressed | Medium
59 | IV | B | I think it is prudent to start out this way, but I could also argue that something like the scenario subset tool is a “nice to have” that the company could also do their own approach to instead. | Rachel Hemphill | Addressed | Low
60 | IV | C | For large and complex models like GOES, a more detailed model component inventory may be helpful. For example, a “Treasury Model” may include the GEMS engine that generates projected rates given initial state variables and model parameters, the tool used to fit the initial state variables from the initial rate curve, a Generalized Fractional Flooring tool, other pre-/post-processing tools, calibration tools (for determining or updating parameters from calibration data), etc. | Connie Tang | Unaddressed | Medium | To address with release of model inventory file.
61 | IV | C | Note that the same underlying models are used to produce different levels of output detail for the Basic and Robust Data Sets, so it would be more natural to identify Treasury, Equity, and Corporate models instead of a “Basic Data Set Model” and “Robust Data Set Model.” | Connie Tang | Revised in latest draft | Low | Removing all references to Robust Data Set
62 | IV | C | Regarding whether the Model Governance Framework should be extended to optional items available for a fee (e.g., Robust Data Set, API tool), we agree that the Model Governance Framework should be extended to all optional items related to the economic scenario generator. | RRC | Revised in latest draft | Low | Document has been revised to remove optional Conning product offerings (API tool, robust data set) from NAIC Governance process to focus on items specific to the Valuation Manual requirements.
63 | IV | C | All aspects of GOES, including (but not limited to) items such as the API tool and generation of the additional elements in the Robust Data Set, should be covered by the model governance policy. There are no other means of establishing governance over these items, and GOES objectives and appropriate statutory reporting will not be achieved if the API is incorrect or Basic and Robust data sets are inconsistent. | Connie Tang | Revised in latest draft | Low | Document has been revised to remove optional Conning product offerings (API tool, robust data set) from NAIC Governance process to focus on items specific to the Valuation Manual requirements.
64 | IV | C | Regarding the posed question, the model governance framework should extend to optional, additional items that are available for a fee. | Connie Tang | Revised in latest draft | Low | Document has been revised to remove optional Conning product offerings (API tool, robust data set) from NAIC Governance process to focus on items specific to the Valuation Manual requirements.
65 | V | A | While not specifically related to governance, we would appreciate a future opportunity to discuss whether proprietary models that comport with the stylized facts and are within the thresholds for targeting criteria and evaluation statistics facts would be acceptable for valuation purposes. We note that developing these thresholds is something ACLI and our team of subject matter experts are currently working so this is a topic we would be willing to present on in the coming weeks. | ACLI | Addressed | High | APF 2025-04 has specific standards for allowing proprietary economic scenario generators that do not involve the acceptance criteria.
66 | V | A.2 | ⦁ The latest set of acceptance criteria includes “targeting criteria” and “evaluation statistics.” These should be defined in the governance framework to clarify how they will be used in determining whether scenario sets are acceptable. ⦁ Prior to making sure model statistics are able to meet the stylized facts and/or acceptance criteria, it should define what is the intended purpose and how the model fits for purpose. ⦁ Who is responsible for determining if a particular scenario set is acceptable? Would this process include interested parties such as ACLI and the Academy? Having more detail on this part of the process may be helpful, acknowledging that judgment will be needed to determine whether scenario set(s) as a whole are appropriate for use in this context. ⦁ Regarding the implementation of material model updates, ACLI notes that depending on the change, some items may not need any formal testing, some could require review from the NAIC model office, and some updates could require full field testing or an off-cycle update across the board in line with section four. The nature of the GOES model changes and limitations of the model offices should also be considered when determining whether model office testing is preferrable to industry field testing. | ACLI | Unaddressed | Medium | Suggest more robust thresholds around acceptance criteria and adaptability in varying economic conditions as day II item.
67 | V | B | We would recommend clarification of who would be performing the model validation along with the frequency at which the model validation is performed and how this would be related to the model risk rating mentioned in Section IV. These appear to be items that should be part of the Model Developer responsibilities. | RRC | Revised in latest draft | High | NAIC and Conning perform model validation on a monthly basis
68 | V | B | To strengthen governance, additional detail and clarification could be added on how certain aspects of the framework will be applied. For example, the following would be helpful: Defined process for how the models will be validated/reviewed, both by Conning and by the NAIC. | ACLI | Revised in latest draft | Medium | Added additional details on NAIC monthly review of model output
69 | V | B | The Governance framework should make clear who specifically is responsible for this process. | ACLI | Revised in latest draft | Low | Added additional detials
70 | V | B | Will validation procedures be performed on all models in the model inventory? How frequently (e.g., for every monthly update)? Performed by whom? Independent of model developer? Does the scope of validation vary depending on the extent of the change or the risk of the model? | ACLI | Revised in latest draft | High | Added additional detials
71 | V | B | We request that Conning produce scenarios across different starting economic environments (most recent year end, low rate, high rate, normal yield curve) when changes are made to the generator to ensure the calibration still meets the criteria in these situations. | ACLI | Revised in latest draft | High | Updated the Output Validation section
72 | V | B | Model validation should also consider including, as applicable: ⦁ Implementation into production (e.g., checking that there are no breakdowns or unintended consequences as the model is moved from the development environment to the production environment) ⦁ Assessment of limitations ⦁ Adequacy of documentation | ACLI | Unaddressed | Medium | request is for additional detail on what documentation will be part of the validation process (what was tested and limitations for example)
73 | V | B.2 | Model replication procedures or a sample prototype should be shared publicly for transparency in-line with V.B.2. | ACLI | Addressed | Medium | NAIC sharing additional workpapers on model review at goes 10/29 meeting.
74 | V | B.2 | We recommend that the description of this testing be clarified as the Model Owner would not necessarily be considered independent. | RRC | Revised in latest draft | Low | Updated
75 | V | B.3 | For output validation, industry would request more specifics on the validation steps and criteria. At minimum, validation should be compared to stylized facts and acceptance criteria, and the validation should be made public. Such validation should also contemplate how the model will perform in different economic environments. | ACLI | Addressed | High | NAIC shared dashboard at 10/29/25 GOES SG meeting
76 | V | B.4 | The model validation section focuses on implementation / process testing. However, model validation must also include confirming the conceptual soundness and suitability of the selected model form and calibration*. *A liability assumption analogy: ⦁ Implementation / process validation would be confirming that the dynamic lapse assumption is implemented according to specifications. E.g., Testing that the single specified linear function, calibrated from in-surrender period lapses and depending only on a nominal definition of in-the-moneyness, has been implemented according to the model documentation. ⦁ Validation of conceptual soundness and suitability would be checking how well the dynamic lapse formula and parameters align with experience, expected relationships, and best practices and satisfy the intended purpose. E.g., Reviewing company experience, industry studies, behavioral research, product features, and sensitivities to determine that the functional form should be an S-curve; have separately calibrated parameters for in-surrender period, shock year, and ultimate lapses; and depend on an actuarial present value definition of in-the-moneyness as well as withdrawal status. | Connie Tang | Unaddressed | High
77 | VI | A | We would appreciate discussion on drawing distinction between the governance applicable for different types of updates. For example, the governance process for recalibration, monthly updates, annual updates, off-cycle model changes, and structural model improvements would be similar, but each should be tailored to the risk and significance associated with each change. | ACLI | Revised in latest draft | Low | Additional detail added to model updates and review.
78 | VI | A | Regarding whether model documentation should be included as appendices in the document so that governance and documentation are all in one place, or if it is preferable to keep them separate, the items should at least be linked but the specific format does not matter as long as it is easily accessible and clearly identified. | ACLI | Addressed | Low | Suggest separate Governance and technical documentation
79 | VI | A | There should be a complete inventory of all initial market inputs, their data sources, and update frequency for the Interest Rate, Equity, and Corporate models. This information would normally be maintained in the model documentation (and not the model governance framework document). | Connie Tang | Addressed | Low | to address in technical docmentation
80 | VI | A | This part should be more explicit. Are only the starting conditions updated and none of the other technical parameters updated? Is the random number seeding consistent month over month? In other words, if all of the starting conditions were the same as the prior month, are the resulting scenarios identical to the previous month? | Matt Cheung | Addressed | Low | to address in technical docmentation
81 | VI | A | The draft document appears to be a hybrid document that establishes policy and documents compliance with policy. However, separate documents stored in a well-cataloged, version controlled, and searchable repository may be easier to understand and maintain – particularly if there are multiple models, model components, or tools and multiple responsible parties. ⦁ Typically, a board or oversight group owns the model risk / governance framework and policies. The framework and policy documents define scope (e.g., models and model components covered), roles and responsibilities, materiality and risk rating thresholds / considerations, and activities required (e.g., documentation, inventories, validation, testing) by materiality / risk rating. Frameworks and policies are subject to periodic review and revision (e.g., every 1-2 years or if regulatory requirements change). The documents tend to be relatively stable, with updates primarily to elements such as materiality or risk rating thresholds. ⦁ Separately, there are documents demonstrating compliance with the policy (e.g., model and model component inventories; detailed technical documentation on data, models, and tools; validation reports and findings; change logs; test plans, results, and signoffs; risk and control assessments and attestations; list identifying the people serving in each role). These documents are updated frequently (e.g., as personnel change or model components are updated). | Connie Tang | Unaddressed | Medium | rquest is for policy documents that change less frequently are usually updated less often and it may be easier to keep in a separate document that the compliance documentation that would be updated more regularly
82 | VI | A | Also, for the companies that pay Conning to license GEMS, is there functionality for those companies to create scenarios using different initial levels? If so, how close would those be to these monthly update resulting scenarios. | Matt Cheung | Addressed | Low | Conning said companies can license GEMS and the scenarios with the same initial levels will match those posted that conning would generate the next month. Clients get more documentation and the ability to shock scenarios. Conning said if there were changes to the Corporate Model those would be included to licensed clients.
83 | VI | B | The annual update might be better characterized as an “Annual Review and Update (if necessary).” Automatic / formulaic parameter updates may not be necessary for the interest rate and equity models and calibrations. The long-term (steady state) interest rate target appears to have been set as a means-to-an-end (i.e., to make the calibration perform better on criteria such as low- and high-for-long) vs. calculated from or strongly tied to historical data. The long-term equity assumption was constrained at “8.75%” based on a long-standing judgment (from 2005 and reaffirmed during GOES) and not directly tied to historical data. Neither of these items seem likely to change meaningfully in a year or with an additional of 12 months of data. (Note: There is insufficient model and calibration information to opine on potential Corporate model updates.) Nevertheless, there should be a formal annual review process. It is an assumption best practice to regularly assess whether there are trends that may be indicative of a change in long-term expectations; review accumulated findings and/or items flagged by ongoing or off-cycle monitoring; and confirm whether updates are warranted. Updates may be needed in some years but not others. However, not making a change is still an actuarial decision, and explicitly affirming that prevents accidental neglect of an assumption (“set-it-and-forget-it until it’s too late”). | Connie Tang | Revised in latest draft | High | Revised Language
84 | VI | B | Regarding annual model updates, how should industry contribute to these? | ACLI | Revised in latest draft | High | Noted that public discussion of any changes from annual review to take place in GOES SG
85 | VI | B | Are they going to offer a set of scenarios old vs new so that companies can do an attribution for initial level updates vs starting other model updates? I would actually like to better understand the sensitivity of annual parameter updates before this goes live. I would think industry would insist there to be something like 90 days for them to test and ‘accept’ the changes like they would for annual updates. Industry may also have a preference for which quarter this is executed in. | Matt Cheung | Revised in latest draft | Medium | Added detail noting that scenario sets would be provided and a minimum 30-day comment period would be implemented to test the scenarios.
86 | VI | B | The draft notes as an example the mean reversion parameter (MRP) could be updated. We are unaware of any methodology being discussed or exposed, so we would appreciate clarity around any updates to this component and other components/parameters of the model. | ACLI | Revised in latest draft | Low | Removed references to annual update of MRP, is now included in 5 year recalibration
87 | VI | B | There should be a defined quarter for annual to avoid unnecessary volatility. | ACLI | Revised in latest draft | Low | Added that annual review updates would target June month-end.
88 | VI | B | Are these generally going to be parameter updates due to an update of the historical calibration data? I think there should be a limit to what can be changed here (i.e. the functional forms of the models should not change). | Matt Cheung | Revised in latest draft | Low | Added detail to note it is only parameter changes that would be considered.
89 | VI | C | The 5-year review should be a comprehensive model review and include assessing the continued suitability of the model form/structure (which may include evaluation of vendor limitations) and not limited to the recalibration of the existing model. The 5-year review process should commence well before 5 years has elapsed. (Starting the process in 5 years would delay any update significantly beyond 5 years.) Special considerations may apply for our initial implementation. If findings related to model limitations and soundness are open / deferred from the initial implementation, it may be advisable to continue exploring enhancements and actions in the coming years (vs. waiting until the formal kickoff of the 5-year review in a few years). | Connie Tang | Revised in latest draft | Low | Added additional detail that the relevant NAIC groups would consider whether the GOES continues to be fit for purpose in 5 year recalibration cycle.
90 | VI | C | We recommend a requirement that the model be reviewed and recalibrated at a minimum every five or so years to confirm continued appropriateness and fit of the model. | RRC | Revised in latest draft | Low | Five-year timeframe has been clarified.
91 | VI | C.2 | I would think functional form model changes should be handled only within the 5y cycle. | Matt Cheung | Revised in latest draft | Low | Clarified that the annual review does not include functional form changes.
92 | VI | C.2 | Ideally we can communicate some sort of minimal timeline for this so industry knows they will have adequate time to evaluate/respond. | Matt Cheung | Revised in latest draft | Low | Added no less than 30 days
93 | VI | D | A clear update process for off-cycle updates should be established. | ACLI | Revised in latest draft | Low | Off-cycle model updates to utilize similar process to the five-year model recalibration.
94 | VI | D | Potential drivers of off-cycle model changes and/or recalibration may include: ⦁ New uses / products / risks that require additional economic outputs or make existing scenario values or characteristics more material ⦁ Changes / enhancements to stylized facts or acceptance criteria ⦁ Conditions that may be indicative of a change in long-term expectations – including but not limited to persistent trends in actual data, Fed / monetary policy changes, fiscal policy changes, market structure changes, global economics ⦁ Conditions the model was not designed to handle or does not handle well occurring more frequently or persistently (e.g., conditions that stress a known model/calibration limitation or simplification beyond what’s acceptable, distributions or sensitivities that no longer make sense because of previously unidentified model/calibration limitations) ⦁ Regime changes not adequately reflected in the ranges of the existing distribution ⦁ Failing and/or worsening performance (e.g., trending towards failure) on acceptance criteria ⦁ Other model findings (e.g., correcting errors, removing an approximation / simplification, enhancements for conceptual improvements and evolving best practices) Errors or market conditions materially “breaking” the existing model/calibration would be more likely to trigger more “immediate” actions. Most other cases would tend to be incorporated into an upcoming annual review / update, and some could even be slated for the next 5-year review. However, there should be regular monitoring and escalation procedures. | Connie Tang | Revised in latest draft | Medium | Updated
95 | VI | E | ACLI would suggest regularly scheduled meetings for discussion about whether there is a need for model or calibration updates. Such discussions could also make it easier to identify items for the 5-year recalibration and model revisions (or sooner if deemed necessary) and off-cycle model updates as described in the draft framework. | ACLI | Revised in latest draft | Medium | Added the model findings discussion to the annual review process.
96 | VII | A | It is unclear how the Model Findings (Section VII) and Model Change (Section VIII) processes will work if the items involved are subject to a non-disclosure agreement. (E.g., Will interested parties be able to ask questions and obtain sufficient information to log a finding or request? How will the findings or changes be posted and discussed?) | Connie Tang | Revised in latest draft | Medium | Individuals can bring concerns to regulators, NAIC staff, and Conning regarding proprietary aspects of the Conning corporate model. If necessary, Conning can relax the NDA restrictions for discussions of specific items that need resolution in a public forum.
97 | VII | A | We haven’t defined model users. | Rachel Hemphill | Revised in latest draft | Low | added model users to the roles and responsiblities table.
98 | VII | B | To strengthen governance, additional detail and clarification could be added on how certain aspects of the framework will be applied. For example, the following would be helpful: Defined methodology for determining a finding’s risk classification and controls to ensure that the finding is corrected appropriately and in a timely manner. | ACLI | Unaddressed | Low
99 | VII | B.1 | The handling and utility of the proposed classification system (Material, Complex; Material, Simple; Immaterial) is unclear. In my experience, findings are typically classified as errors or refinements and assessed on a several dimensions. The classification and assessment then lead to an explicit recommended action (e.g., address immediately, address at the next scheduled [annual, 5-year] review / update, monitor and address at some pre-defined trigger). Error vs. Refinement The first distinction is whether a finding is an error or refinement (e.g., changes to address previously documented model limitations, simplifications, approximations or reflect emerging situations, advancements, best practices). Errors should be “addressed immediately” while refinements are typically scheduled over longer time frames. Addressing an error may mean fully implementing the correction, implementing a workaround / topside / adjustment that reduces the impact below an immateriality (de minimus) threshold, or potentially documenting and having an implementation plan (with appropriate monitoring in the interim) if the error is already under an immateriality threshold. Errors also trigger reviews to identify root causes and any control deficiencies requiring remediation. (We must fix the error and make sure that controls are adequate to mitigate the risk of similar future errors.) Assessment Each finding may be assessed on several dimensions, e.g, ⦁ Materiality / significance: potential dollar or percentage impact on reserves, surplus, or RBC ratios for representative model office blocks and estimated company results ⦁ Likelihood: number of companies affected, how frequently the finding may have an impact (e.g., possible but rare, intermittent, often in the current or specifically identifiable environment, all the time) ⦁ Complexity and effort / resources required to address. Findings should be evaluated both individually and in aggregate to make sure that smaller (seemingly immaterial) items do not add up to something material in aggregate. | Connie Tang | Revised in latest draft | Medium | Revised Language
100 | VII | B.3 | I don’t know what this phrase means. That delay can’t potentially make it more material? | Rachel Hemphill | Revised in latest draft | Low | added clarifying language to illustrate that it cant be a problem that is small now but could become material over time.
101 | VII | B - Discussion | As a starting point, ACLI believes that items such as financial impact, reputational impact, and operational efficiency (including documentation inefficiency) should be considered. | ACLI | Revised in latest draft | Low | addressed
102 | VII | B - Discussion | Prioritization and Taking Action The error / refinement determination and impact assessment result in the assignment of an actionable rating (e.g., address immediately, as soon as practicable, at the next annual update, at the next 5-year review). Findings with more material and/or likely impacts would generally receive the highest prioritization and timeliest implementation. Practical considerations (e.g., complexity, effort, logical grouping of related changes) may influence the exact timing / scheduling, but critical or high priority items (e.g., high severity and frequency) would still be addressed with urgency. The shared and “closed” / proprietary nature of GOES may complicate prioritization decisions and remediation activities. For example, an error or refinement that is immaterial or only moderately impactful at the industry level may be very material for a small company or a company with a particular product or asset strategy. The PBR Actuary will need detailed and timely information about the issue and its potential remediation to determine if additional actions may be required in the interim (e.g., building or using other generators/models to assess impacts, adjusting reserves/capital). Ideally, scenario sets with the corrections/refinements and/or prototype models implementing or approximating the proposed changes would be provided as part of the GOES assessment process. Note that using a prior version of the generator would be an option only if the finding is a newly introduced error, and the prior version happens to be correct. (This should not be a common occurrence in an effective control environment.) | Connie Tang | Addressed | Medium
103 | VII | B - Discussion | Given Conning develops and owns the model, in addition to relying on the GOES subgroup and interest parties to identify the issues/model findings, we suggest NAIC form a smaller/independent technical group to review Conning’s technical update for reasonability or unintended consequences. | ACLI | Unaddressed | High
104 | VIII | A | For “emergency” model findings and fixes, we recommend that an escalation process be created such that critical model fixes can be implemented in a timely manner, when the normal NAIC approval process may not be fast enough | RRC | Revised in latest draft | Medium | Added additional language
105 | VIII | A | "Routine (monthly) changes” that trigger some sort of exception handling should require notification / tracking. (E.g., Substituting or not updating for an unavailable or questionable input data element, deviating from the publicly documented algorithm for setting initial state variables because a valid or acceptable solution could not be found, altering credit model adjustments because they no longer work well) | Connie Tang | Unaddressed | Medium
106 | VIII | A | A governance policy should define what “full governance” might entail for each type of finding and regular update type (i.e., monthly, annual, 5-year) – including the testing, validation, documentation, and approvals required and when model office testing, impact studies, and full field testing would apply. | Connie Tang | Revised in latest draft | Low | Added a definition of “full governance” and added model office testing guidance to 5-year recalibration and annual review.
107 | VIII | A | The policy should identify how often model change requests will be reviewed and prioritized. (Avoids having requests that languish.) | Connie Tang | Revised in latest draft | Low | Added language on an expected resolution date for each item.
108 | VIII | D | Again, this addresses the “models” from Conning but not NAIC (analysis tools) | Rachel Hemphill | Revised in latest draft | Low | Added section on NAIC Analysis and review tools.
109 | VIII | D | Information about development, test, and production IT environments would more commonly be found in testing and/or controls documentation and not a model governance framework or policy document. (However, the current draft appears to be a hybrid document and not purely a framework/policy document.) A policy document would establish expectations for types of testing, test plans, and documentation (potentially by change type and/or risk level) instead of leaving testing to “the discretion of the model developer and owner.” The use of development, test, and production environments is standard in both software and model development, but the process described for storing, tracking, and promoting models appears to deviate from standard software development practice and insurance company modeling best practices / IT control requirements. Formal version control / library management software and processes should be used to store, track, and promote all model components (e.g., source code, Excel tools, pre-/post-processing tools) as well as inputs (e.g., initial market, calibration parameter, and projection parameter files) through the different IT environments. (For example, development of the next version should start from the “gold copy” of the production model in the repository instead of copied from whatever may reside in the production environment.) The current draft mentions developer testing. However, it is unclear if or how other standard software and model testing processes (e.g., integration testing, user acceptance testing) are being performed. | Connie Tang | Unaddressed | Medium
110 | VIII | F | To strengthen governance, additional detail and clarification could be added on how certain aspects of the framework will be applied. For example, the following would be helpful: Standards for what information should be included in documentation. Since model changes can have a significant impact to model users, transparency of communication/documentation and timely disclosure to users is important. | ACLI | Addressed | Low | NAIC and Conning are in progress in making enhancements to each component of the documentation. Interested parties will be able to provide feedback on the documentation.
111 | IX |  | ACLI members have also identified questions due to the proprietary nature of certain aspects of the model, particularly the Corporate Model. ⦁ It is common practice for companies to replicate models to help manage their business (e.g., projecting future reserves / capital requirements for capital / risk management). We are concerned that an NDA would restrict this ability; we would be comfortable if the NDA explicitly prohibits the documentation from being used for any purpose external to the company or for commercial purposes. ⦁ Further, it is unclear how ACLI could have discussions related to aspects of the generator that are proprietary. If not all of our members have signed an NDA, it would seem we would not be able to discuss those items at all. This would also be an issue for any public discussions. | ACLI | Addressed | Medium | 1) Companies can be given access to additional corporate model documentation when they sign an NDA. However, this additional access does not allow the company to replicate Conning’s proprietary model. 2) Individuals can bring concerns to regulators, NAIC staff, and Conning regarding proprietary aspects of the Conning corporate model. If necessary, Conning can relax the NDA restrictions for discussions of specific items that need resolution in a public forum.
112 | IX |  | We would also like to take this opportunity to remind you of a fundamental concern we have with the black box nature of the GEMS Corporate Bond model. We have much better control over a process that uses our own internal generator than a process that relies on a black box. It is also a more efficient and flexible process to have one source of economic scenarios for managing our business, a source that we understand and can use on demand. Today we are able to test our own internal scenario generator against the fully transparent AIRG model to ensure that the scenarios generated from our internal model do not result in a TAR that is materially lower than the TAR resulting from the use of the prescribed generator, consistent with the requirements of VM-21. From our conversations with Conning, we understand that we will not be allowed to replicate their Corporate Bond Model for the purposes of testing our internal model, even if we sign an NDA. This raises serious concerns and is inconsistent with the requirements of VM-21 and with messages we heard at various LATF meetings that sufficient documentation would be released. | John Hancock | Addressed | Medium | John Hancock’s understanding is correct. Companies can be given access to additional corporate model documentation when they sign an NDA. However, this additional access does not allow the company to replicate Conning’s proprietary model.
113 | IX |  | We suggest including clarification of a vendor’s access to Conning’s Software Documentation Library if a company outsources the work to a vendor and the vendor signs Conning’s Nondisclosure Agreement | RRC | Addressed | Medium | clarified
114 | X |  | Regarding the people identified as having access to models and documentation, we recommend that Conning and the NAIC consider mitigants to key person risk and clarify any succession plans in place to ensure that there will be appropriate resources to update the models. | RRC | Unaddressed | High
Note on E102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start here for DG call following 3/5/25 discussion.