## GOES SG Meeting Plan
Timing | Meeting Discussion Topic | Milestone | Notes
2023-12-18 | Kick-off Call for GOES (E/A) Subgroup | • NAIC and Oliver Wyman Perform Model Office Testing • Circulate any promising scenario sets. Individual Companies with capacity that wish to do so are encouraged to test using their own models and share results with regulators. • GOES Subgroup calls to review scenario statistics against acceptance criteria, review model office results. • Adopt Final Stylized Facts and Acceptance Criteria. Conning to recalibrate if regulators have substantial edits
2023-12-25
2024-01-01
2024-01-10 | Scenario Stratification and Statistics
2024-01-17 | Equity-Treasury Linkage
2024-01-24 | Corporate Model Quantitative Comparison
2024-01-31 | 1. SERT Scenario Methodology 2. Treasury Flooring Methodology |  | NAIC Committee Assignments (TBD, based on 2023 timing)
2024-02-07 | Preliminary Model Office Testing Results
2024-02-14 | Valuation Dates and Other Field Test Parameters
2024-02-21 | Discuss Model Calibration
2024-02-28 | Valuation Manual and RBC Instruction Changes
2024-03-06
2024-03-14 |  | Present Model Office Results, Expose Scenario Set(s). | NAIC Spring National Meeting
March - June |  | Unaggregated GOES Field Test (VM-20, VM-21/C3P2, and C3P1), If Needed
June-July |  | Reg-Only Company Presentations of Unaggregated GOES Field Test (VM-20, VM-21/C3P2, and C3P1) Results, If Needed
July-Sept |  | VM-22 Field Test
Formulas:
Timing = [Timing, row above]+7

## Scenario Stratification
Scenario Picker Tool Goal:
· Provide scenario subsets that are reasonably representative of the full 10,000 scenario set for policies and/or contracts that are sensitive primarily to interest rates, equities, or both.
Scenario Picker Tool Decision Points:
1. Decision Point: Should there be a scenario picker that is included as part of the economic scenario generator?
Drafting Group Recommendation: Yes, with understanding that single methodology would not address all potential use cases.
2. Decision Point: Should custom stratifications be allowed, for both VM-20 and VM-21, if the company provides an off-cycle or model office comparison between the subset and full 10,000 to show there is not material understatement or bias?
Drafting Group Recommendation: Yes. This may reduce the importance of having a perfect response for items #3-#5 below.
3. Decision Point: What size of subsets are needed?
Original Proposal: 50, 200, 1000, 2000.
Drafting Group Discussion: Requests were made for additional 500 and 5,000 scenario sets, but the potential for a tool to produce custom # scenario sets may mitigate the need to produce numerous scenario sets with different numbers of scenarios.
4. Decision Point: Should there be stratification based on interest rates and/or equity?
Original Proposal: There should be two or three versions of the scenario picker tool, which stratify scenarios based on interest rate, equity, and/or both.
Drafting Group Recommendation: Allow for option to stratify based on interest and equity.
5. Decision Point: For interest rates, what tenor(s) should be used for stratification?
Proposal: This may be a limitation in the current scenario picker tool. Consider multiple metrics based on different tenors.
No Drafting Group Recommendation
6. Decision Point: What metric should be used for stratification?
Proposal: Evaluate whether the current scenario picker’s metric is reasonable, aside from its narrow focus on a specific interest rate tenor.
No Drafting Group Recommendation