## GOES SG Meeting Plan
Timing | Meeting Discussion Topic | Notes
2025-01-29 | 1. Discuss Revised Initial Yield Curve Fitting and DGFF modifications to GOES 2. Consider Formation of a GOES Model Governance Drafting Group
2025-02-05 | Discuss Comments on Model Governance Framework | *May be meeting of GOES Model Governance Drafting Group
2025-02-12 | 1. Discuss Revised Eqiuty Calibration 2. Discuss GOES VM Amendment 3. Consdier referrals to VACR SG and LRBC WG
2025-02-19 | Suggest GOES Model Governance Framework DG Meeting
2025-02-26 | Discuss Model Office Results of Latest GOES Updates
2025-03-05 | 1. Discuss SERT Scenario, DR and Scenario Statistics Exposure 2. Discuss Sensitivity Scenario Exposure
2025-03-12 | No Meeting
3/22-3/23 | NAIC Spring National Meeting LATF Session
Formulas:
Timing = [Timing, row above]+7

## Project Plan
GOES Implementation Timeline
Project start date: | 2024-09-30 |  |  | Legend: |  | On track |  | Low risk |  | Med risk |  | High risk |  | Unassigned
Scrolling increment: | 0
Milestone description | Category | Start | Days | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31
1900-02-27
GOES Project Plan
Discuss GOES Calibration and Determine any Changes | On Track | 2024-09-25 | 90
Perform Model Office Testing on Material GOES Model Changes | On Track | 2024-11-30 | 91
NAIC Fall National Meeting | Milestone | 2024-11-15 | 16 | bar: 2024-11-30
Draft and Discuss Valuation Manual Amendments | On Track | 2025-01-31 | 150
NAIC Spring National Meeting, Discuss Model Office Results | Milestone | 2025-03-22 | 10 | bar: 2025-03-31
LATF Adoption of Valuation Manual Amendments | Milestone | 2025-06-30 | 1 | bar: 2025-06-30
A Committee Adoption of Valuation Manual Amendments | Milestone | 2025-07-31 | 1 | bar: 2025-07-31
NAIC Summerl National Meeting, Adoption of VM Amendments by Exec/Plen | Milestone | 2024-10-15 | 1
GOES Effective for Valuation Manual | Milestone | 2026-01-01 | 31 | bar: 2026-01-31
Draft and Discuss RBC Blanks Changes | On Track | 2025-07-31 | 240
RBC Changes Need to be Exposed by 3/31 to be effective for YE 26 | Milestone | 2026-03-31 | 1 | bar: 2026-03-31
Life RBC Working Group Adopts RBC Changes | Milestone | 2026-05-31 | 1 | bar: 2026-05-31
To add more data, Insert new rows ABOVE this one

## Sheet1 (hidden)
2025-01-15
2025-01-22
2025-01-29 | Discuss SERT Scenario, DR and Scenario Statistics Exposure
2025-02-05 | GOES Scenario Stats
2025-02-12 | Discuss Comments on Model Governance Framework
2025-02-19 | Consider Exposure of GOES VM Amendment
2025-02-26 | Discuss Model Office Results of Latest GOES Updates
2025-03-05
2025-03-12
2025-03-19 | No Meeting
2025-03-26 | Week of National Meeting
2025-04-02 | No Meeting
2025-04-09
2025-04-16
2025-04-23
2025-04-30
2025-05-07
2025-05-14
2025-05-21
2025-05-28
2025-06-04
2025-06-11
2025-06-18
2025-06-25 |  | All Valuation Manual Amendments will need to be adopted by this time
2025-07-02
2025-07-09
2025-07-16 |  | Approximate Date For A Committee Meeting
2025-07-23
2025-07-30 | No Meeting
2025-08-06 | Week of National Meeting
2025-08-13 | No Meeting
2025-08-20
2025-08-27
2025-09-03
2025-09-10
2025-09-17
2025-09-24
2025-10-01