## GOES SG Meeting Plan
Timing | Meeting Discussion Topic | Notes
2024-09-25 | Draft Model Governance Draft Framework Exposure
2024-10-02 | Discussion of Feedback on: 1. UST, Equity, and Corporate Scenarios/Calibration 2. UST Flooring
2024-10-09 | Discussion of Feedback on: 1. Initial Yield Curve Fitting 2. SERT Scenarios
2024-10-16 | Discussion of Feedback on: 1. Scenario Selection 2. Availability of Sensitivity Scenarios
2024-10-23 | Conflict with LRBC WG - Cancel or Reschedule
2024-10-30 | Hold for likely continuation of prior topics
2024-11-15 | NAIC Fall National Meeting LATF | Comments on Model Governance Draft will be discussed
Formulas:
Timing = [Timing, row above]+7

## Project Plan
GOES Implementation Timeline
Project start date: | 2024-09-30 |  |  | Legend: |  | On track |  | Low risk |  | Med risk |  | High risk |  | Unassigned
Scrolling increment: | 0
Milestone description | Category | Start | Days | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31
1900-02-27
GOES Project Plan
Discuss GOES Calibration and Determine any Changes | On Track | 2024-09-25 | 90
Perform Model Office Testing on Material GOES Model Changes | On Track | 2024-11-30 | 91
NAIC Fall National Meeting | Milestone | 2024-11-15 | 16 | bar: 2024-11-30
Draft and Discuss Valuation Manual Amendments | On Track | 2025-01-31 | 150
NAIC Spring National Meeting, Discuss Model Office Results | Milestone | 2025-03-22 | 10 | bar: 2025-03-31
LATF Adoption of Valuation Manual Amendments | Milestone | 2025-06-30 | 1 | bar: 2025-06-30
A Committee Adoption of Valuation Manual Amendments | Milestone | 2025-07-31 | 1 | bar: 2025-07-31
NAIC Summerl National Meeting, Adoption of VM Amendments by Exec/Plen | Milestone | 2024-10-15 | 1
GOES Effective for Valuation Manual | Milestone | 2026-01-01 | 31 | bar: 2026-01-31
Draft and Discuss RBC Blanks Changes | On Track | 2025-07-31 | 240
RBC Changes Need to be Exposed by 3/31 to be effective for YE 26 | Milestone | 2026-03-31 | 1 | bar: 2026-03-31
Life RBC Working Group Adopts RBC Changes | Milestone | 2026-05-31 | 1 | bar: 2026-05-31
To add more data, Insert new rows ABOVE this one