## Workplan
Ref # | Priority | Expected Completion Date | Tasks Working Group (includes regulator only meetings and open meetings (back to back) | Charge | Decision Points | Comments from Interested Parties | Info for White Paper
|  | Before 2023 Fall National Meeting |  | A. Review state insurance privacy protections regarding the collection, data ownership and use rights and disclosure of information gathered in connection with insurance transactions and make recommended changes, as needed, to certain NAIC models, such as the NAIC Insurance Information and Privacy Protection Model Act (#670) and the Privacy of Consumer Financial and Health Information Regulation (#672). | Regulator Only vs. Open Meeting: Regulators discuss regulator-prepared draft in closed meeting and agree to suggested revisions. A draft is exposed for public comment for 2 weeks prior to discussion and consideration of adoption during open meeting. |  | Draft document (White Paper) on data ownership and use rights
|  | Ongoing Task | The Group will receive updates from NAIC staff and review state/federal/international applications as appropriate. | Engage with federal and international supervisors and agencies on efforts to manage, evaluate, monitor and regulate consumer data privacy as technology changes continue to evolve. | Frequency of updates; Determining whether a response is neede to ongoing developments
1 |  | Expose workplan timeframe and deliverables for public comment 3/23/22 | Review, discuss, and finalize exposure draft of work plan and deliverables for public comment. | Agenda for the Spring National Meeting: Introduction of WG members; State and Federal Privacy Legislation Updates; Discuss and Consider for Adoption PPWG Workplan, Timeframe and Deliverables. | Regulator Only meetings 3/9/22 & 3/23/22 |  | Request information from companies and consumer reps about consumer data ownership and usage for White Paper?
2 |  |  |  | Focus on 2 specific workstreams: |  |  | Talk to Commissioner Birrane to focus the work on the white paper.
Revisions to NAIC Privacy Models: (Model 670 First; then 672)
White Paper on data ownership and use rights: with instructions, history, explanation about why we did what we did, etc.
3 |  | Before the Spring National Meeting (March 2022) | Solicit/assign regulator volunteers who will meet separately to draft suggested revisions to each section. | Model 670 (how data is collected): Preamble and 24 Sections. | Revisions needed: Yes or No. If Yes, add in regulator session; expose 2 weeks for public comment; discuss and adopt revisions during that open meeting.
MO670_041520_ExposureDraftTopics_with_042920_CommentsonSec1-9_rev082221.pdf posted on PPWG Webpage includes EXPOSURE DRAFT TOPICS – APRIL 15, 2020 (and definitions from Model #668-IDSM) WITH APRIL 29, 2020 COMMENTS ON SECTIONS 1- 9 as of 8/22/21
NAIC Spring National Meeting 3/22-3/25
4 |  |  | 3/23/22: (1) Finalize our workplan; (2) Discuss the goals of the white paper; (3) Make assignments for Sections 1-3 (due by 4/6); (4) subgroup to develop 4-6 questions to give to interested parties to elicit comments on data use and ownership rights (due 5/4). | MO 670 | Break the sections into smaller drafting groups | March 23: Expose the workplan and goals for comment; discuss the goals of the white paper as outlined by Com. Barrane
5 |  |  | 4/13/22:(1) Review drafts for Sections 1-3 and make any necessary changes;(2) Make assignments for Sections 4-7.(due May4) | Preamble
Section 1. Scope
|  |  |  | Section 2. Definitions | Replace existing definitions with applicable IDSA Model 668 definitions? | April 13: Expose drafts for Sections 1-3 for comments (due May 4)
|  |  |  | Section 3. Pretext Interviews | Do we still need this provision?
6 |  |  |  | Section 4. Notice of Insurance Information Practices | Should we coordinate this with notices in Model 672?
|  |  | 5/11/22: (1) Discuss comments on draft of Sections 1-3 and make appropriate changes; (2) Discuss drafts of Sections 4-7 and make appropriate changes; (3) Make assignments for Sections 8-10 (due June 1) | Section 5. Marketing and Research Surveys | Coordinate this with Model 672? | May 11: Expose drafts for Sections 4-7 for comments (due June 1) | 5/11/22: Expose request comments from the industry to questions.regarding data ownership and use rights (due 6/8)
Section 6. Content of Disclosure Authorization Forms
Section 7. Investigative Consumer Reports
7 |  |  | 6/8/22: (1) Discuss comments on drafts for Sections 4-7 and make appropriate changes; (2) Review drafts of Sections 8-10 and make appropriate changes; (3) Make assignments for Sections 11-13 (due July 7) | Section 8. Access to Recorded Personal Information | Coordingate with Model 672? | June 8: Expose drafts of Sections 8-10 for comments (due July 7)
Section 9. Correction, Amendment or Deletion of Recorded Personal Information
Section 10.Reasons for Adverse Underwriting Decisions
8 |  |  | 7/13/22: (1) Discuss comments on drafts for Sections 8-10 and make appropriate changes; (2) Review drafts of Sections 11-13 and make appropriate changes; (3) Make assignments for Sections 16, 17, and 20 (due August 10) | Section 11. Information Concerning Previous Adverse Underwriting Decisions |  | July 13: Expose drafts of Sections 11-13 for comments (due August 10)
Section 12.Previous Adverse Underwriting Decisions
|  |  |  | Section 13.Disclosure Limitations and Conditions | Coordinate this withModel 672?
9 |  |  | The WG should discuss whether these sections should be amended. | Section 14.Power of Commissioner
Section 15.Hearings, Witnesses, Appearances, Production of Books and Service of Process
10 |  | 2022 Summer National Meeting (8/9 -8/12) | Required: Model Law Request Form to EX for approval | Report from the Privacy Protections (H) Working Group to the H Committee | Upon approval, WG has 1 year and 1 national meeting to complete. An extension is not desirable, but can be requested .
11 |  |  | 8/17/23: (1) Discuss coments on drafts for Sections 11-13 and make approprite changes; (2) Review drafts of Sections 16, 17, & 20 and make appropriate changes; (3) Make assignments for Sections 21 & 22 (due September 7) | Section 16.Service of Process - Insurance Support Organizations |  | August 17: Expose drafts of Sections 16, 17, & 20 for comments (due September 7) | Draft of white paper on data use and ownership rights available for WG to review (due 8/10/22)
Section 17.Cease and Desist Orders and Reports
12 |  |  | The WG should discuss whether these sections should be amended or removed | Section 18.Penalties | Should we delete these provisions? These topics are dependent on state law.
Section 19.Judicial Review of Orders and Reports
11 |  |  | See 8/17/23 above | Section 20.Individual Remedies |  | See August 17 above
13 |  |  | September 14: (1) Discuss comments on drafts for Sections 16, 17, & 20 and make appropriate changes; (2) Review drafts of Sections 21 & 22 and make appropriate changes; (3) Discuss whether Sections 14, 15, 18, 19 should be reviewed and make appropriate assignments (due October 5). | Section 21.Immunity |  | September 14: Expose drafts of Sections 21 & 22 for comments (due October 5)
Section 22.Obtaining Information Under False Pretenses
14 |  |  | October 12: (1) Discuss comments on drafts for Sections 21 & 22 and make appropriate changes; (2) Discuss drafts for any of Sections 14, 15, 18, 19, if applicable and make appropriate changes. | Section 23.Severability | Should we delete these provisions? These topics are most likely dependent on state law. | October 12: If changes were made to Sections 14, 15, 18, 19, expose those drafts for comments (due November 2). | Regulator comments and suggested changes due October 7
Section 24.Effective Date
15 |  |  | November 9: (1) If applicable, discuss comments to any changes made to Sections 14, 15, 18, or 19 and make appropriate changes; (2) Review the draft of the white paper and make necessary changes in preparation to expose it for comment. |  |  |  | 12/7/22: Expose draft white paper on data ownership and use rights for comments (due 3/1/2023)
16 |  |  | December 7: Discuss which sections of Model 672 we requiring further review and revision |  |  |  | 12/7 Expose draft white paper on data ownership and use rights for comments (due )
17 |  | 2022 NAIC Fall National Meeting (12/12-12/15) | Required: Project History. | Report from the Privacy Protections (H) Working Group to the H Committee
|  | 1/1/2023-10/30/23: WG will complete its review and revisions of Model 672 |  | Model 672 (How data is used after it's collected) - | MO672_redline082221.pdf - posted on PPWG webpage - has 27 Sections in six Articles and 2 Appendices (52 pages - last 8 are federal notices) |  | 1/1/2023 - 10/30/2023: WG reviews the comments to the draft white paper and makes any necessary amendments as the WG finishes its work on Model 672. any changes will be exposed for comment.
|  |  |  | ARTICLE I. GENERAL PROVISIONS | Work on General Provisions together?
|  |  | 3/15/2023: (1) Review the workplan for the year; (2) discuss the comments on the draft of the white paper; (3) make assignments for Article 1 (due 4/12) | Section 1. Authority
Section 2. Purpose and Scope
Section 3. Rule of Construction
|  |  |  | Section 4. Definitions | Replace existing definitions with IDSA Model 668 definitions?
|  | NAIC Spring National Meeting 3/22-3/25 |  | Report from the Privacy Protections (H) Working Group to the H Committee
|  |  | 4/19/2023: Review and make appropriate changes to the draft of Article I; (2) mank assignments for Article II (due 5/10/23) | ARTICLE II. PRIVACY AND OPT OUT NOTICES FOR FINANCIAL INFORMATION
Section 5. Initial Privacy Notice to Consumers Required
Section 6. Annual Privacy Notice to Customers Required
|  |  |  | Section 7. Information to be Included in Privacy Notices |  | 4/19/23: Article I revisions exposed for comments (due 5/10/23)
Section 8. Form of Opt Out Notice to Consumers and Opt Out Methods
Section 9. Revised Privacy Notices
Section 10. Privacy Notices to Group Policyholders
Section 11. Delivery
|  |  | 5/17/2023: Review comments on draft of Article I and make appropriate changes; (2) discuss the draft of Article II and make appropriate changes; (3) make assignments for Article III (due 6/7/23) | ARTICLE III. LIMITS ON DISCLOSURES OF FINANCIAL INFORMATION | Determining whether action is needed to support state adoption | 5/17/23: Expose draft of Article II revisions for comments (due 6/7/23)
Section 12. Limitation on Disclosure of Nonpublic Personal Financial Information to Nonaffiliated Third Parties
Section 13. Limits on Redisclosure and Reuse of Nonpublic Personal Financial Information
Section 14. Limits on Sharing Account Number Information for Marketing Purposes
|  |  | 6/14/2023: Reveow the comments on the draft of Article II and make appropriate changes; (2) discuss the draft revisions to Article III and make appropriate changes; (3) make assignments for Article IV (due 7/5/23) | ARTICLE IV. EXCEPTIONS TO LIMITS ON DISCLOSURES OF FINANCIAL INFORMATION | Incorporate FAST Act Changes from Bulletin? | 6/14/23: Expose the draft of Article III for comments (due 7/5/23)
Section 15. Exception to Opt Out Requirements for Disclosure of Nonpublic Personal Financial Information for Service Providers and Joint Marketing
Section 16. Exceptions to Notice and Opt Out Requirements for Disclosure of Nonpublic Personal Financial Information for Processing and Servicing Transactions
Section 17. Other Exceptions to Notice and Opt Out Requirements for Disclosure of Nonpublic Personal Financial Information
|  |  | 7/12/2023: Review the comments on the draft of Article III and make the appropriate changes; (2) review the draft changes for Article IV and make appropriate changes; (3) make assignments for Article V (due 8/2/23) | ARTICLE V. RULES FOR HEALTH INFORMATION | State Regulators can add requirements to HIPAA as needed, but cannot remove requirements. | 7/12/23: Expose the draft revisions to Article IV for comments (due 8/2/23)
Section 18. When Authorization Required for Disclosure of Nonpublic Personal Health Information
Section 19. Authorizations
Section 20. Authorization Request Delivery
Section 21. Relationship to Federal Rules
Section 22. Relationship to State Laws
|  |  | 8/9/2023: Review the comments on the draft of Article IV and make appropriate changes; (2) review the draft revsisons to Article V and make appropriate revisions; (3) make assignments for revisions to Article VI and any revisions to the white paper as a result of changes to Model 672 (due 9/6/23) | ARTICLE VI. ADDITIONAL PROVISIONS |  | 8/9/23: Expose the draft revisions to Article V for comments (due 9/6/23)
Section 23. Protection of Fair Credit Reporting Act
Section 24. Nondiscrimination
Section 25. Violation
Section 26. Severability
Section 27. Effective Date
|  |  |  | Appendix A Sample Clauses | Delete Sample Clauses? Delete Safe Harbor?
|  |  |  | Appendix B Federal Model Privacy Form | Changes to Federal Model Privacy Form?
|  | NAIC Summer National Meeting 8/13-8/17 |  | Report from the Privacy Protections (H) Working Group to the H Committee
|  |  | 9/13/2023: (1) Review comments on draft revisions to Article V and make appropriate changes; (2) review the draft revisions to Article VI and make appropriate revisions; (3) review revisions to the white paper on data use and ownership rightsand make any necessary changes |  |  | 9/13/23: Expose the draft revisions to Article VI for comments (due 10/5/23) | 9/13/23: Expose any revisions made to the white paper on data use and ownership rights for comments (due 10/5/23)
10/12/23: (1) Reviw comments on the draft revisions to Article VI and make appropriate changes; (2) review the revisions to the draft white paper and make appropriate changes.
|  | 2023-10-31 | All drafts completed and sent to Lois to prepare for the Fall National Meeting
|  | 2023 NAIC Fall National Meeting 11/28-12/4 | 11/30: Fall National Meeting: (1) Project history; (2) draft changes to Model 670; (3) draft changes to Model 672; draft white paper on data ownership and use rights