## 2026 Target Timeline
PBR VM-22 Project Draft Timeline
EFFECTIVE DATE GOALS
| 2026-01-01 | PBR VM-22 effective with three year transition period | [14 empty] | 2029-01-01 |  |  |  |  | PBR VM-22 mandatory prospectively
DRAFT TIMELINE | time axis 2021-12-21 to 2025-08-21
# |  | 2021-12-21 | 2022-01-21 | 2022-02-21 | 2022-03-21 | 2022-04-21 | 2022-05-21 | 2022-06-21 | 2022-07-21 | 2022-08-21 | 2022-09-21 | 2022-10-21 | 2022-11-21 | 2022-12-21 | 2023-01-21 | 2023-02-21 | 2023-03-21 | 2023-04-21 | 2023-05-21 | 2023-06-21 | 2023-07-21 | 2023-08-21 | 2023-09-21 | 2023-10-21 | 2023-11-21 | 2023-12-21 | 2024-01-21 | 2024-02-21 | 2024-03-21 | 2024-02-21 | 2024-03-21 | 2024-04-21 | 2024-05-21 | 2024-06-21 | 2024-07-21 | 2024-08-21 | 2024-09-21 | 2024-10-21 | 2024-11-21 | 2024-12-21 | 2025-01-21 | 2025-02-21 | 2025-03-21 | 2025-04-21 | 2025-05-21 | 2025-06-21
1 | SPA DG - develop assumptions/methodology
2 | VM22 SG calls - Address comment letters and edits
3 | ESG Field Test #1
4 | Second VM-22 exposure
5 | NAIC National Meeting December 12 - 15, Tampa FL
6 | ESG Field Test #1 Analysis
7 | Discuss comments from Fall VM-22 draft exposure
8 | SPA Drafting by Subgroup Members
9 | SPA Structure Exposure
10 | VM-31 Drafting by Subgroup Members
11 | Discuss Comments on SPA Structure Exposure
12 | VM-31 Exposure
13 | Discuss Comments on VM-31 Structure Exposure
14 | ESG Field Test #2
15 | ESG Field Test #2 Presentations
16 | VM-22 and C3P1 Field Test
17 | Compile/analyze Field Test results
18 | Discuss field test results on public calls
19 | Resolve outstanding items and changes from field test
20 | LATF exposure and discussion
21 | LATF Adoption
22 | A Committee Adoption
23 | NAIC Exec & Plenary Adoption

## Comment Log - SPA Exposure
NAIC VM-22 Drafting Discussion Log - 2023 SPA Exposure
# | Topic | Description | Date | Tier | Outcome
1 | Aggregation | Clarification on whether payout & accumulation reserving categories are not aggregated for SPA | 2023-11-08 | 1 | Subgroup expressed that the intention is not to aggregate across different reserving categories within the SPA; No edits requested
2 | DR & SPA | Clarification on whether contracts with a DR are subject to the SPA | 2023-11-08 | 1 | Subgroup agreed to keep the DR within the scope of the SPA, with language will be added to clarify DR will calculate a scenario reserve instead of CTE
3 | Inflation | Leave as a fixed rate or follow treasury path, when applying inflation retrospectively to expenses? | 2023-11-08 | 3 | For now, will plan to leave retrospective inflation as a fixed rate
4 | GAPV prior to utilization | Vary calculation of guaranteed value based on whether the guarantee has been exercised or not? | 11/8/2023 & 12/12/2023 | 3 | Subgroup voted to include Academy principle-based wording, with adjustments to emphasize prudence/efficiency
5 | Integrated GAPV | Calculate one GAPV for multiple benefits | 2023-11-08 | 2 | Retained Academy proposed wording and methodology to calculate an integrated GAPV for multiple guarantees
6 | GAPV Application | Is the GAPV only applicable to deferred annuities? | 2023-11-08 | 3 | Adding wording to clarify that the GAPV is not applicable when there is no account value or no surrender benefits
7 | GLWB Utilization | Assume initial utilization percentage, rather than 100% utilization percentage upon exercising guarantee? | 2023-11-08 | 3 | Retained Academy wording for "initial percentage taken" on withdrawals and current credited rate/option budget; Academy to propose disclosures
8 | SPA for no CSV | How is the SPA applied for products with no cash surrender value? | 2023-11-15 | 1 | Adding wording to clarify that the withdrawal and surrender sections are not applicable to products without withdrawal and surrender benefits
9 | Withdrawals for Lifetime GLBs | Clarification on whether "lifetime" GLBs should be specified for the treatment described in Section 6.C.4.c | 2023-11-15 | 3 | Adding the word "lifetime", consistent with the original intention for the draft
10 | Dynamic Lapse - Distribution Channel | Should dynamic lapses vary by distribution channel? | 2023-12-13 | 3 | Exposed drafting group formula, Academy formula, and NYS DFS Special Considerations Letter formula
11 | Base and Dynamic Lapse Rates | Calibrate base lapse rates in tandem with development of dynamic lapse formula | 2023-12-13 | 3 | Exposed drafting group formula, Academy formula, and NYS DFS Special Considerations Letter formula
12 | Zero Dynamic Lapses | Allow dynamic lapses to go down to zero? | 2023-12-13 | 2 | Exposed drafting group formula, Academy formula, and NYS DFS Special Considerations Letter formula
13 | GAPV Discount Rate | Could discount rate for GAPV to determine ITM be redundant if not well-parametrized? | 2023-12-13 | 3 | Exposed drafting group formula, Academy formula, and NYS DFS Special Considerations Letter formula
14 | MVAs | Dynamic lapses to consider MVA features, free partial withdrawals, and standard non-forfeiture? | 2023-12-13 | 2 | Exposed drafting group formula, Academy formula, and NYS DFS Special Considerations Letter formula
15 | Crediting Rate Limit | Intended to only apply to FIA or all products? | 2023-11-15 | 2 | Intended to apply to all products; wording is being added to clarify
16 | Regulatory approval for Crediting Rate | Remove language on regulatory approval for limiting the crediting rate, since simplification section already covers? | 2023-11-15 | 3 | Subgroup agreed to remove the language and add a drafting note expressing openness to proposed wording that addresses persistency bonuses
17
18
19
20

## Comment Log - 2022 Exposure
NAIC VM-22 Drafting Discussion Log - 2022 Exposure
# | Topic | Description | Date | Tier | Outcome
1 | Exemption Threshold Level | Discuss potential reserve thresholds, below which companies can apply for VM-22 exemption | 2023-03-01 | 1 | Subgroup voted for $1b threshold for an individual company; to confirm whether the intent is $2b threshold for a group of companies
2 | Exemption Reinsurance Treatment | Are the reserves for the exemption levels gross or net of reinsurance? | 2023-03-01 | 1 | Subgroup voted in favor of setting a threshold on a gross of reinsurance basis
3 | Longevity Reinsurance k-factor Approach | Consider principles-based methods for longevity reinsurance requirements? | 2023-04-12 | 1 | Subgroup reaffirmed direction of k-factor requirements
4 | GLB Exemption Eligibility | Allow GLBs to be eligible for the exemption? Only if in payout status? What if only the GLB piece is reinsured? | 2023-04-12 | 2 | Subgroup decided to keep language; interested parties may comment if unclear GLB utilization won't make a closed block ineligible for exemption
5 | Include "Other" category in exemption? | Include the "other" category for individual and group annuities in the annual statement for the exemption? | 2023-04-12 | 2 | Will include business from "other" category if falling into scope of VM-22
5 | VM-21 vs. VM-22 Applicability | For principles in Section II, say "shall follow" or "generally expected to follow"? | 2023-04-12 | 2 | Subgroup voted to say "shall follow"
6 | Combo Product Valuation | Should nursing riders and combo products be valued under PBR or prior formulaic reserves? | 2023-04-19 | 2 | Keep nursing home benefits in text; combination products to have living benefits valued with base policy modeled reserve
7 | Reserving Category for GLB with Depleted AV | Use principle-based categorization or require a specific reserving category? | 2023-04-19 | 2 | Voted to prescribe the accumulation reserving category for guaranteed living benefits with depleted fund value
8 | Frequency of Reviewing PBR Assumptions | Current text specifies reviewing experience annually, but assumptions periodically - align the two? Every 3 years? | 2023-04-19 | 2 | Voted to replace "periodically" with "annually" and add a guidance note to consider guidance on full studies
9 | Rider Valuation | Add "After issuance" for determining whether a rider's reference to base policy results in valuing them together? | 2023-04-26 | 3 | Keeping "After issuance" for clarity
10 | Two Benefits in a Contract | "May" or "should" assume the more valuable of two benefits in a contract? | 2023-04-26 | 3 | Per discussion, changed to say "should generally be assumed"
11 | Longevity Reinsurance Premium Frequency | Remove the statement specifying that premiums are paid over the life of the annuitant? | 2023-04-26 | 3 | Kept the statement, but added the word "generally" to provide flexibility to the definition
12 | Separate Account References | Remove references to the Separate Account in VM-22? | 2023-04-26 | 3 | Decided to strike references to separate account, but will add a drafting note to pose a question in field test for referencing separate accounts
13 | Guidance Note in Section 3.A | Make guidance note part of formal text? | 2023-04-26 | 3 | Removed guidance note and make statement part of the formal text
14 | Aggregation within each Reserving Category | Clarifying guidance on aggregation within reserving categories | 2023-04-26 | 3 | Added reference to both DR and SR, and moved to aggregation subsection within Section 3
15 | Revisiting Aggregation | View expressed that a more principles-based approach for aggregation | 2023-04-26 | 3 | Will include the impact of aggregation in field testing; no other changes
17 | Annuitization from Other Host Contracts | VM-21 vs. VM-22 treatment for annuitizations from host contracts | 2023-04-26 | 3 | Will work with ACLI to consider specific recommendations, and decide whether to work through the VM-22 Subgroup or LATF (impacts VM-21)
18 | Supplementary Contracts | Need a definition for supplementary contracts? | 2023-04-26 | 3 | Voted to not add a definition or SSAP reference for supplementary contracts
16 | Pre-determined Reinsurance Premiums | If premiums are pre-determined for longevity reinsurance, how does the k-factor approach apply? | 2023-05-10 | 3 | ACLI will gather specific questions and proposed modifications on the k-factor methodology, and a separate call will be dedicated to this topic
19 | Index Credit Hedge Margin | Determine prescribed minimum margins | 2023-05-10 | 3 | Will revisit after LATF addresses this issue for VM-21; alternatively, will revisit after further information is gathered through field testing
20 | Projection Period | No obligations or not material obligations at the end of the projection period? | 2023-05-10 | 3 | Decided to keep the language as "no obligations remaining"
21 | MVA Threshold | Should there be a percentage threshold of market value assets in a portfolio to determine MVA treatment? | 2023-05-10 | 3 | Will not specify a certain percentage, but rather say "all" assets must be held at market value for the MVA to apply to the CSV floor
22 | Longevity Reinsurance Guidance Note | Clarify guidance note saying that deterministic assumptions are not appropriate for longevity reinsurance | 2023-05-10 | 3 | To remove guidance note
23 | Term Certain in SPIA SET exemption | Include "Annuities Certain" and "Supplementary Contracts" from Exhibit 7 in SPIA threshold definition? | 2023-05-24 | 3 | Agreed to include Annuities Certain and Supplementary Contracts in the payout annuity threshold and scope definitions
24 | PRT Exclusion Testing treatment | Keep ineligibility for PRT and longevity reinsurance to automatically pass exclusion test through SPIA carveout? | 2023-05-24 | 3 | Subgroup expressed openness to reviewing a future proposal by the ACLI that permits certain types of longevity reinsurance and PRT to be eligible
25 | SPIAs with increasing benefits & optionality | Allow SPIA exclusion test treatment to include fixed COLA, 50% joint, non-elective changes) rather than 5% standard | 2023-05-24 | 3 | Agreed to use ACLI proposed language, but only carve-out cost of living adjustments and joint/survivor benefits
26 | Payout Annuity Exemption Definition | Remove group annuities from payout exemption reserve definition if excluding PRT/reinsurance from carveout? | 2023-05-24 | 3 | ACLI will include proposed language consistent with future proposal on permitting certain types of longevity reinsurance and PRT to be eligible
27 | Index vs. Non-Index Hedging Bifurcation | What if a company does not clearly separate hedging strategies for index vs. non-index hedge programs? | 2023-05-10 | 3 | Will revisit after LATF addresses this issue for VM-21; alternatively, will revisit after further information is gathered through field testing
28 | Hedging Investment Policy | Include VM-21 wording that clarifies the hedging program must be consistent with investment policy? | 2023-05-24 | 3 | Subgroup agreed to include VM-21 wording related to a company's investment policy for its hedging program
29 | E Factor Examples | Clarify examples listed for the E-factor for hedging purposes is non-exhaustive? | 2023-06-13 | 3 | Agreed to add sentence from VM-21 that clarified the list being non-exhaustive.
30 | Sensitivity Test Immateriality | Include assumptions that are deemed to be immaterial? (e.g., account transfers, etc.) | 2023-06-13 | 3 | Decided to leave unchanged, in which "account transfers" and "future deposits"
31 | Less Conservative Than Experience | Refer to credibility and materiality instead of "clear evidence"? | 2023-06-13 | 3 | Agreed to change "clear evidence" to "credible evidence"

## Comment Log - 2021 Exposure
NAIC VM-22 Drafting Discussion Log - 2021 Exposure
# | Topic | Description | Date | Tier | Outcome
1 | VM-22 Scope and Definitions | Keep current definitions for what is in-scope or focus only on non-variable annuities out of scope | 4/13/2022, 10/4/2022 | 1 | Exposed principles in Section II of the Valuation Manual, moved definitions to VM-01, and removed references to product names in VM-22 section 2
2 | Reserving categories and aggregation | Determine Option 1 or Option 2 from exposed reserve category definitions | 2022-04-13 | 1 | Preliminary vote to pursue Option 1
3 | Small Company Exemption | Fixed Annuity PBR exemption, similar to life PBR exemption for smaller carriers? | 4/13/2022, 10/4/2022 | 1 | Voted to pursue a "Fixed Annuity PBR Exemption"; Exposed ACLI proposed threshold based on prior year reserves, with some modifications
4 | Reinvestment Guardrail | Keep VM-20/VM-21 mix, Academy mix, TX mix, or other? Wait until field test for final decision? | 2022-04-27 | 1 | Wait until observing impact in field testing results before voting on a reinvestment mix guardrail
5 | Principles & Risks Across VM Chapters | Build one section in the Valuation Manual for principles that apply to VM-20, VM-21, and VM-22 | 2022-04-27 | 2 | Openness to interested party proposals for a common "principles" section, but will focus on working through other VM-22 decisions before exploring
6 | General Assumptions Section | Add a section to the VM-22 draft on general considerations and requirements for assumption | 2022-04-27 | 2 | Will include a proposed general assumptions section ("Section 13") from Texas, to be consistent with a recent APF adoption on VM-21
7 | Transition Period | Permit 1) early adoption and 2) retrospective adoption to the start of the 3-year transition period? | 2022-04-27 | 2 | Decided to not pursue early adoption; VM-22 will say silent on retrospective adoption to start of transition period, similar to VM-20
8 | Minimum Error for Index Credit Hedges | What should be the minimum breakage expense (i.e., error) for modeling hedges supporting index credits? | 2022-05-11 | 2 | Will wait until seeing field testing results before minimum threshold
9 | Longevity Reinsurance | How should longevity reinsurance be defined and treat negative reserves/recurring premiums? | 2022-05-11 | 2 | Academy presented on longevity reinsurance and will provide a refined definition; New Jersey proposal is exposed for reserving requirements
10 | Categories for VM-31 Disclosures | What level of granularity should be required for disclosing PBR reserves for product groups in VM-31? | 2022-05-11 | 2 | Will wait until seeing field testing results before determining granularity of disclosures
11 | Exclusion Test: SPIA contracts | Allow SPIAs to have the option of PBR vs. pre-PBR valuation without an exclusion test? | 2022-06-01 | 2 | Voted to allow SPIAs automatically pass exclusion testing, subject to criteria around optionality and a liability duration threshold (TBD)
12 | Exclusion Test: PRT Certification Method | Allow PRT contracts to use the Certification Method for exclusion testing? | 2022-06-01 | 2 | Do not allow PRT to undergo the Certification Method
13 | Exclusion Test: Grouping | Group between products with significantly different risk profiles? | 2022-06-01 | 2 | Do not allow grouping between products with significantly different risk profiles, consistent with VM-20 and TDI's proposal
14 | Exclusion Test: Future Premiums | For the stochastic exclusion ratio test, determine whether to include future premiums | 2022-06-01 | 2 | Include future premiums in the numerator, but only benefits and expenses in the denominator, consistent with VM-20.
15 | Exclusion Test: Deterministic Reserve | To pass the deterministic test, does the company need to pass or disclose 16 scenarios with baseline mortality? | 2022-06-01 | 2 | Require passing the ratio test for 16 economic scenarios under 100% of the anticipated experience mortality assumption
17 | Import Reinsurance Wording from VM-20 | Import VM-20 wording on incorporating contractual or additional characteristics for modeling reinsurance? | 2022-06-14 | 2 | Include proposed wording from VM-20
18 | Fair Value Certification | Include fair value certification, similar to existing VM-21 requirement? | 2022-06-14 | 2 | Include fair value certification disclosure for non-index credit hedging programs
16 | PRT Mortality | Permit PRT mortality with limited credibility to follow a third-party provider instead of an industry table? | 2022-06-14 | 2 | Voted in favor of using a prescribed table; do not permit a third party table upon limited credibility
19 | Allocation Method | Determine Option 1 or Option 2? Wait until observing field test results before deciding? | 2022-09-21 | 2 | Using an ACLI proposal based on Option 2 for the VM-22 exposure, which addresses a tax issue for non-life contingent annuities
20 | Working Reserve | Use a working reserve concept to serve as a floor for contracts without cash surrender value? | 2022-06-29 | 2 | Academy will work on a working reserve concept for contracts without cash surrender value, though may be little impact due to reserving categories
21 | Grouping for Fund Value Depletion | Appropriate reserving category for deferred annuities with GMWBs/GMIBs that have depleted fund value | 2022-06-29 | 2 | Decided to leave these contracts in the "Payout Reserving Category" for now, but will add a drafting note to solicit feedback an optional approach
22 | RBC Guidance Note | Retain the guidance note in VM-21 that discusses the relationship between reserves and RBC? | 2022-08-17 | 3 | ACLI will provide the full text for the Subgroup to consider
23 | Principle 1 | Should the edits to Principle 1 for VM-22 be incorporated into VM-21 as well? | 2022-08-17 | 3 | For now, will plan to focus only on VM-22, as LATF can explore the other VM chapters upon the Subgroup's recommendation of the VM-22 draft to LATF
24 | Principle 2 | Does setting an SR to be reasonably conservative over a span of economic cycles contradict other principles? | 2022-07-13 | 3 | ACLI will provide the full text for the Subgroup to consider
25 | Aggregation Limits | Guidance note stating aggregation may not be possible for experience rated group and reinsurance treaties | 2022-07-13 | 3 | Will include this text in the VM-22 draft
26 | Principle 3 | Delete "Generally, assumptions are to be based on the conservative end of the confidence interval"? | 2022-07-13 | 3 | Retain this language
27 | Principle 5 | Delete sentence about the principle to not reduce the reserve unless reducing the risk? | 2022-07-13 | 3 | Retain this language
28 | Risks not reflected | Retain or remove the list of "Risks not reflected" in VM-22? | 2022-07-13 | 3 | Remove subsection 3, but keep section 4 and update title to include "risks not reflected"
29 | Separate Account References | Recommendation to delete all references to "separate accounts" in VM-22 | 2022-07-13 | 3 | For now, will keep references to "separate accounts" and will add a drafting note to solicit feedback
30 | Combination Risks | Proposal to delete "Risks modeled in the company’s risk assessment processes that are related to the contracts" | 2022-07-13 | 3 | Retain this language
31 | Immaterial Risks | Recommendation to delete sentence about not reflecting risks that do not materially affect the reserves | 2022-07-13 | 3 | Remove this language
32 | Liquidity Risk | Refer to liquidity risks for "run on bank" or "sudden and significant levels of withdrawals and surrenders" | 2022-07-13 | 3 | Use the "run on bank" description
33 | Significant Future Reserve Increases | Strike this item from the list of risks not reflected? | 2022-07-13 | 3 | Retain this language
34 | Fixed Annuity Definition | Need to define a "fixed annuity"? | 2022-07-13 | 3 | Will replace all references to "fixed annuity" with "non-variable annuity"
35 | Longevity Swaps | Are these contracts included in the definition of PRT? | 2022-07-13 | 3 | As a follow-up, Academy will include reviewing the definition of PRT when revisiting the definition of longevity risk
36 | CSV and GMDB definitions | Retain VM-21 definitions for "cash surrender value" and "guaranteed minimum death benefits"? | 2022-07-13 | 3 | Will not retain the definition for "cash surrender value" and will move the "guaranteed minimum death benefits" to VM-01
37 | Assumed reserve level for RBC | Question whether CTE70 was the assumed level for reserves upon determining RBC | 2022-07-19 | 3 | Question relates to RBC, and therefore did not discuss as part of the VM-22 Subgroup
38 | VM-23 | Consider reinstating "VM-23" to avoid confusion around the where exemptions/exclusions point to vs. PBR? | 7/19/2022, 10/4/2022 | 3 | Exposed moving the current VM-22 requirements (previously Section 14 in the VM-22 draft) to a separate “VM-V” section in the Valuation Manual.
39 | Pre-Reinsurance | Request to develop further guidance around pre-reinsurance | 2022-07-19 | 3 | ACLI will consider whether to provide suggested language to clarify pre-reinsurance cash flow requirements in response to the next exposure
40 | Deterministic Reserve | Use this term for the single scenario reserve calculated upon passing the deterministic exclusion test? | 2022-07-19 | 3 | Will replace “scenario reserve” with “deterministic reserve”. Also added “aggregate minimum reserve” as the term for the final reserve
41 | Deterministic Certification Option | Keep this terminology or change? | 2022-07-19 | 3 | Given that the term "deterministic reserve" will not be used, decided to keep this terminology
42 | Stochastic Exclusion Test | Change Section 3.E to "Stochastic Exclusion Test" header? | 2022-07-19 | 3 | Accepted comment and made change to update header
43 | Guidance Note for Exclusion Test | Remove the guidance note that clarifies that AG33/AG35 may be used upon passing the exclusion test | 2022-07-19 | 3 | Decided to remove this guidance note
44 | Prudent Estimate Assumptions | Move Section 3.G to Section 4 of the document? | 2022-07-19 | 3 | Subgroup decided to hold off for now
45 | Simplifications | Port over VM-21 Section 3.H on simplifications, approximations, and modeling efficiency techniques? | 2022-07-19 | 3 | Subgroup agreed to add this wording for simplifications, to be consistency with VM-21
46 | Review experience every three years? | Make this a requirement for the qualified actuary? | 2022-07-19 | 3 | Subgroup agreed to include a requirement to review experience every three years
47 | Simplification example for the SPA | Add an example of a simplification for the SPA upon development | 2022-07-19 | 3 | Delete for now and revisit upon development of the SPA
48 | Stochastic Mortality | Consider including stochastic mortality in the stochastic reserve for longevity reinsurance? | 2022-07-19 | 3 | Subgroup agreed to port over VM-20 language on stochastic modeling when static prudent estimates are not appropriate for liability assumptions
49 | MVA Guidance Note | Is the market value adjustment guidance note from VM-21 still appropriate for VM-22? | 2022-08-17 | 3 | Subgroup decided to remove guidance note
50 | Hedging Reorganization | Move parts of Section 4.A.4 to Section 9, which covers hedging | 2022-08-17 | 3 | Open to comments on restructuring this section during the next exposure
51 | Future Hedging Programs | Align VM-22 draft to be consistent with APF 2020-12 adopted edits for VM-21? | 2022-08-17 | 3 | Subgroup decided to be consistent with APF 2020-12 language
52 | Index Credit Hedge Margin | Does this reflect both model risk and real-world error? How does stress testing justify the error? | 2022-08-17 | 3 | Wording is added to state that both sources of error are reflected in the margin; in addition the reference to stress testing will be removed
53 | Margin on Hedging Paragraph | Remove this paragraph if included in another section, even upon edits from TDI/OPBR? | 2022-08-17 | 3 | Open to comments on restructuring this section during the next exposure
54 | Revenue Sharing | Is the section of revenue sharing applicable to non-variable products? | 2022-08-17 | 3 | Decided to retain this section
55 | Projection Period | Use consistent language with VM-20? | 2022-08-17 | 3 | Kept the first sentence to be consistent with VM-20, but removed the second proposed sentence, since now the approximation section has been added
56 | PIMR | Include pre-tax IMR in VM-22? | 2022-08-17 | 3 | Refer to LATF
57 | MVA on CSV Floor | Apply the market value adjustment factor to the cash surrender value reserve floor for applicable products? | 2022-09-07 | 3 | Will not add language applying the MVA to the CSV floor; instead new language states the MVA shall only apply when assets are held at market value
58 | Consistency with Managed Business | Modify NAER requirement to have assets modeled in a manner consistent with how business is managed? | 2022-08-24 | 3 | ACLI will consider whether to recommend specific edits related to this comments
59 | Limits on NAER | Define a specific cap or floor for the NAER instead of saying it should not be "unreasonably high"? | 2022-08-24 | 3 | Subgroup decided to modify language to change "unreasonably high" to "extremely positive or negative", which covers both directions
60 | Reserve Floor | NY comment on using CARVM as a reserve floor | 2022-08-24 | 3 | Will hold off on discussing the standard projection amount until after the other sections of VM-22 are re-exposed, in Fall of 2022
61 | Longevity Reinsurance & SPA | Require the k-factor approach to address negative reserve issue for longevity reinsurance in SPA? | 2022-08-24 | 3 | Will hold off on discussing the standard projection amount until after the other sections of VM-22 are re-exposed, in Fall of 2022
62 | Standard Projection Amount | Equitable comment on supporting SPA with company assumptions insignificant risk factors | 2022-08-24 | 3 | Will hold off on discussing the standard projection amount until after the other sections of VM-22 are re-exposed, in Fall of 2022
63 | Exclusion Testing & SPA | Modify exclusion test to address the standard projection amount? | 2022-08-24 | 3 | Will hold off on discussing the standard projection amount until after the other sections of VM-22 are re-exposed, in Fall of 2022
64 | Hedging eligibility for exclusion testing | Refine wording around the restriction for not allowing blocks with hedging programs to use exclusion testing? | 2022-08-24 | 3 | Academy will suggest possible disclosures to better identify “hedging programs solely supporting index credits”
65 | Mortality Stress Tests | If using the NY7 for the Certification Method, add mortality stress scenarios? | 2022-08-24 | 3 | Added language for mortality stress scenarios if using the NY7 Certification Method
66 | Mortality Shock | Include the mortality shock for the ratio test based on the company materiality standard if more restrictive? | 2022-08-24 | 3 | No objections to modifying the stochastic exclusion ratio test to use the company materiality standard if more restrictive
67 | Baseline Mortality Test | Include the baseline mortality test in determining the exclusion test? | 2022-06-01 | 3 | Subgroup agreed to include the baseline mortality scenario for the stochastic exclusion ratio test
68 | Permutations | Include note on number of exclusion test permutations for clarity? | 2022-06-01 | 3 | Updated guidance note to include the number of permutations, inclusive of testing economic scenarios under the mortality baseline
69 | Non-Proportional Reinsurance | Add definition for non-proportional reinsurance | 2022-08-24 | 3 | Decided to add a guidance note that references the APPM for clarification on the non-proportional reinsurance
70 | SERT if Other Tests Fail | Prohibit passing the SERT if the demonstration test fails? | 2022-08-24 | 3 | Added language to prohibit passing the stochastic exclusion ratio test if the demonstration test fails
71 | Demonstration Test | Remove options in 1.a and 2.a? | 2022-08-24 | 3 | ACLI will take back and decide whether to recommend removing the demonstration test altogether, or only certain components/language
72 | Deterministic Exclusion for SPA | Consider SPA for the deterministic exclusion test | 2022-08-24 | 3 | Will hold off on discussing the standard projection amount until after the other sections of VM-22 are re-exposed, in Fall of 2022
73 | Deterministic Exclusion Scenario | Is the deterministic certification intended not be applicable for blocks with index credit hedging? | 2022-09-07 | 3 | Intent is for the deterministic certification option to not apply to also not apply to hedging programs supporting index credits; no changes made
74 | SPIA Guidance Note | Remove guidance note specifying that the deterministic exclusion test applies to SPIAs? | 2022-09-07 | 3 | No objections to removing guidance note
75 | Delta Hedging | Replace or remove example about delta hedging for VM-22? | 2022-09-07 | 3 | Remove example referring to delta hedging
76 | Non-Elective Benefits | Remove guidance note to limit modeling non-elective benefits after CSV is depleted if reducing reserves? | 2022-09-07 | 3 | No objections to language, but removed guidance note because the similar wording already existed in the paragraph above
77 | 100% Policyholder Efficiency | Assuming 100% policyholder inefficiency contradicts VM Section II 6.H.2, so revise VM Section II? | 2022-09-21 | 3 | Replace VM Section II language with the principle that efficiency increases over time
78 | NGE Board of Directors | Comment that only allowing NGE exclusion if approved by the Board does not necessarily seem reasonable | 2022-09-21 | 3 | Removed this language from the draft, but added a drafting note to inquire on why potential language may be appropriate
79 | Unsupported Judgement | Comment to remove the reference to using "unsupported actuarial judgement" from Section 11 | 2022-09-21 | 3 | No objections to removing this language
80 | Mortality and Reinsurance | Does Section 11.A require evaluation of a plus vs. minus segment differently for pre- vs. post reinsurance? | 2022-09-21 | 3 | This language is not included in VM-21 and was removed from the VM-22 draft
81 | Mortality Improvement | Is the mortality improvement requirement intended to apply to all mortality assumptions in VM-22? | 2022-09-21 | 3 | Addressed by clarifying that this section only applies to industry mortality assumptions
82 | Option 1 DR vs SR | Require separate allocation for DR vs. SR for allocation Option 1 (Section 13)? | 2022-09-21 | 3 | Agreed to add wording to clarify the allocation between the DR and SR should be separate
83 | Option 2 for Direct Iteration Method | Option 2 is not designed to work for the Direct Iteration Method | 2022-09-21 | 3 | ACLI will consider adding language to address the direct iteration method
84 | Option 2 Single Scenario | Could produce unstable allocation when products with different risk profiles are aggregated for PBR | 2022-09-21 | 3 | Reserving categories will require separate allocation for payouts and accumulation-based annuities
85 | Index-linked annuity | This term is used in the proposed Section II, Subsection 2 draft, but is not defined | 2022-10-04 | 3 | Implicitly addressed through the proposed set of principles for scope of VM-21 vs. VM-22 in Section II of the Valuation Manual
86 | Modified Guaranteed Annuities (MGAs) | VM-21 has language that exempts contracts falling under scope of MDL-255; does this contradict Section II edits? | 2022-10-04 | 3 | Implicitly addressed through the proposed set of principles for scope of VM-21 vs. VM-22 in Section II of the Valuation Manual