## Workplan 6-29-22
Charge | Decision Points
A. Review state insurance privacy protections regarding the collection, data ownership and use rights and disclosure of information gathered in connection with insurance transactions and make recommended changes, as needed, to certain NAIC models, such as the NAIC Insurance Information and Privacy Protection Model Act (#670) and the Privacy of Consumer Financial and Health Information Regulation (#672). | Regulator Only vs. Open Meeting: Regulators discuss regulator-prepared draft in closed meeting and agree to suggested revisions. A draft is exposed for public comment for 2 months prior to discussion and consideration of adoption during open meeting.
Engage with federal and international supervisors and agencies on efforts to manage, evaluate, monitor and regulate consumer data privacy as technology changes continue to evolve. The Group will receive updates from NAIC staff and review state/federal/international applications as appropriate. | Frequency of updates; Determining whether a response is needed to ongoing developments
Re-write of NAIC Privacy Model(s): (Models 670 and 672)
Model # 670 | Model 672 (How data is used after it's collected) -
Preamble | Section 1. Authority
Section 1. Scope | Section 2. Purpose and Scope
Section 3. Rule of Construction
Section 2. Definitions | Section 4. Definitions
Section 4. Notice of Insurance Information Practices | Section 5. Initial Privacy Notice to Consumers Required
Section 6. Annual Privacy Notice to Customers Required
Section 7. Information to be Included in Privacy Notices
Section 8. Form of Opt Out Notice to Consumers and Opt Out Methods
Section 9. Revised Privacy Notices
Section 10. Privacy Notices to Group Policyholders
Section 11. Delivery
Section 5. Marketing and Research Surveys | Section 12. Limitation on Disclosure of Nonpublic Personal Financial Information to Nonaffiliated Third Parties
Section 13. Limits on Redisclosure and Reuse of Nonpublic Personal Financial Information
Section 14. Limits on Sharing Account Number Information for Marketing Purposes
Section 15. Exception to Opt Out Requirements for Disclosure of Nonpublic Personal Financial Information for Service Providers and Joint Marketing
Section 16. Exceptions to Notice and Opt Out Requirements for Disclosure of Nonpublic Personal Financial Information for Processing and Servicing Transactions
Section 17. Other Exceptions to Notice and Opt Out Requirements for Disclosure of Nonpublic Personal Financial Information
Section 8. Access to Recorded Personal Information
Section 9. Correction, Amendment or Deletion of Recorded Personal Information
Section 6. Content of Disclosure Authorization Forms | Section 18. When Authorization Required for Disclosure of Nonpublic Personal Health Information
Section 19. Authorizations
Section 20. Authorization Request Delivery
Section 10.Reasons for Adverse Underwriting Decisions
Section 11. Information Concerning Previous Adverse Underwriting Decisions
Section 12.Previous Adverse Underwriting Decisions
Section 13. Adverse UW Notice
Section 3. Pretext Interviews
Section 7. Investigative Consumer Reports
Section 14.Power of Commissioner | Section 21. Relationship to Federal Rules
Section 15.Hearings, Witnesses, Appearances, Production of Books and Service of Process | Section 22. Relationship to State Laws
Section 16.Service of Process - Insurance Support Organizations | Section 23. Protection of Fair Credit Reporting Act
Section 17.Cease and Desist Orders and Reports | Section 24. Nondiscrimination
Section 18.Penalties | Section 25. Violation
Section 19.Judicial Review of Orders and Reports
Section 20.Individual Remedies
Section 21.Immunity
Section 22.Obtaining Information Under False Pretenses
Section 23.Severability | Section 26. Severability
Section 24.Effective Date | Section 27. Effective Date

## Meeting & Due Dates
Due Dates and Meetings-Drafting Model 670 and Model 672
2022 | 2023 | 2023
Drafting June 15, 2022 - September 2, 2022 (Weekly meetings of the drafting group; regular exposure to the WG & IRs for comment) | Drafting Group Makes Recommendations to WG (based on comments received) - February 13, 2023 - February 28, 2023 | Make Additional Revisions to Revised Draft Models based on NAIC Legal Review - June 20, 2023 - June 30, 2023
Vote on Model Law Request (Permission to Open Models 670 and 672 for Revision) -Tuesday, August 2 @ 1:00 pm EDT | Revised Draft Models Exposed for Additional Comments March 1, 2023 - March 29, 2023 | Send Revised Draft Models to WG, IRs, & Interested Parties for Additional Comments- June 30, 2023 - July 14, 2023
Editor Subgroup Review - September 2, 2022 - September 26, 2022 (Exposure to WG & IRs when completed) | NAIC Spring National Meeting - Discuss Revised Draft Models (Mar 22 - Mar 25) | Distribute Additional Comments to WG, IRs, & Interested Parties - July 15, 2023
Drafting Group Makes Revisions -September 27, 2022 - October 10, 2022 | Revisions Made to the Draft Models Based on Comments Received - March 30 - April 14 | Discuss Revised Models Comments from WG, IRs, & IP - July 19, 2023
Draft Models Sent to WG & IRs for Comments - October 12, 2022 - November 4, 2022 (draft models will be shared as soon as the revisions are completed) | Revised Draft Models Sent to WG & IRs for Comments - April 14, 2023 - May 5, 2023 | Post Revised Draft Models -July 28, 2023
Regulator-only Meeting to Discuss WG & IRs' Comments - November 9, 2022 | Drafting Group Makes Needed Additional Revisions to Draft Models - May 8, 2023 - May 12, 2023 | Vote on the Revised Draft Models - NAIC Summer National Meeting (August 13 - August 17)
Drafting Group Makes Changes - November 10, 2022 - November 18, 2022 | Regulator Only Meeting - Discuss IP Comments on the Revised Draft Models - May 17, 2023
Draft Models sent to NAIC Legal for Review - November 29, 2022 | Make Additional Revisions to Revised Draft Models based on Comments from WG & IRs - June 2, 2023 - June 6, 2023
Draft Models Posted for Interested Parties' Comments - December 9, 2022 - February 10, 2023 | Send Revised Draft Models to NAIC Legal for Review - June 6, 2023 - June 19, 2023
Due Dates and Meeting - White Paper on Data Ownership and Use Rrights
2022 | 2023 | 2023
Surevey Distributed - July 1, 2022 | Comments from Interested Parties on Draft White Paper Due - February 24, 2023 | Post Revised Draft White Paper For Comments from WG, IRs, & Interested Parties - June 23, 2023 - July 14, 2023
Survey Responses Due - July 28,2022 | Regulator-only Meeting to Discuss Interested Parties' Comments -March 8, 2023 | Meeting - Discuss Revised White Paper Comments - July 19, 2023
Update on Survey Responses - 2022 Summer National Meeting in Portland, OR (Tues., Aug. 9 @ 12:30 pm Pacific) | NAIC Spring National Meeting - Discuss Draft White Paper (March 22 - March 25) | Additional Revisions (if needed) to Revised Draft White Paper in Response to Comments July 20- July 23
Survey Responses Compiled - September 1, 2022 | Drafting Group Revisions to Draft White Paper Based on Interested Parties' Comments Due April 14, 2023 | Post Revised Draft White Paper - July 24, 2023
Draft White Paper sent to WG & IRs - October 1, 2022 | Distribute Revisions to Draft White Paper to WG & IRs for Comments- April 17, 2023 - May 15, 2023 | Vote on the Revised Draft White Paper - NAIC Summer National Meeting (August 13 - August 17)
WG & IR Comments on Draft White Paper Due - October 28, 2022 | Distribute WG & IR Comments to the WG and IRs - May 16, 2023
Regulator-only Meeting to Discuss WG & IR Comments - November 2, 2022 | Regulator Only Meeting - Discuss IP Comments & Revisions to Draft White Paper - May 17, 2023
Request NAIC Legal Revview of Draft White Paper - November 9, 2022 | Send Revised Draft White Paper to NAIC Legal for Review - May 22, 2023 - May 30, 2023
Draft White Paper Exposed for Comments from Interested Parties - December 2, 2022 | Make Revisions to Revised Draft White Paper Based on NAIC Legal Review - May 31, 2023 - June 9, 2023